## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME | SM/14910 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000697/2022-2023 | 582/BWD | 17/02/2023 | 17/02/2024 | PUSPA ENTERPRISE | 1185.88 | 174.57 | 14.72 | 73
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME | SM/14910 | New | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 1244/BWD | 17/03/2023 |  | Resource Division | 7.44 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME | SM/14910 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 1965/BWD | 26/04/2023 |  | Resource Division | 2.89 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME | SM/14910 | New | Material Requisition To Resource Division |  |  | RTOR000810/2023-2024 | 300/BWD | 24/01/2024 |  | Resource Division | 20.47 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME | SM/14910 | New | New service connection charges of Gohagram W/S Scheme TW-2 |  |  | BILL/00690/2023-2024 | BP-2023-24-32 | 26/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.55 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME | SM/14910 | New | NEW SERVICE CONNECTION FOR GOHAGRAM PWSS TW 1. |  |  | BILL/02489/2023-2024 | BP-2023-24-539 | 15/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.94 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME | SM/14910 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME | SM/14910 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOHAGRAM Water Supply Scheme [ Block- MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000123/2023-2024 | 2640/CMD | 14/06/2023 | 14/07/2023 | CHOUDHURY ENTERPRISE | 27.48 | 0 | 0 | 0
Total | [13 empty] | 1315.7 | 174.57 | 13.27