## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari - II | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | MOSHRA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000387/2023-2024 | 3196/BWD | 24/07/2023 | 23/07/2024 | M/S LOKE NIRMAN | 285.22 | 47.73 | 16.73 | 60
2 | PURBA BARDHAMAN | Memari - II | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) |  |  | ORD/000985/2023-2024 | 2561/BSD | 30/10/2023 | 04/01/2024 | MD HASIN | 0.85 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari - II | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | Material Requisition To Resource Division |  |  | RTOR000345/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 9.91 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari - II | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | Material Requisition To Resource Division |  |  | RTOR000469/2023-2024 | 3993/BWD | 08/09/2023 |  | Resource Division | 7.17 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari - II | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | Material Requisition To Resource Division |  |  | RTOR000678/2023-2024 | 5053/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari - II | Central Mechanical | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | Quotation for new service connection for Mashra PWSS TW-2 |  |  | BILL/00297/2024-2025 | BP-2024-25-147 | 19/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.84 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari - II | Central Mechanical | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | Electric quotation for New Service Connection at Moshra W/S Scehem PH-I. |  |  | BILL/01782/2023-2024 | BP-2023-24-289 | 26/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.54 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari - II | Central Mechanical | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari - II | Central Mechanical | MOSHRA PIPED WATER SUPPLY SCHEME | SM/14931 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Moshra Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000714/2023-2024 | 4025/CMD | 29/08/2023 | 28/09/2023 | MAA KALI ENTERPRISE | 29.37 | 4.2 | 14.3 | 50
Total | [13 empty] | 400.35 | 51.93 | 12.97