## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | PASCHIM NABAGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer ,JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000177/2023-2024 | 3069/BWD | 18/07/2023 | 17/07/2024 | SRI RAM CONSTRUCTION | 473.94 | 140.48 | 29.64 | 25
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | Material Requisition To Resource Division |  |  | RTOR000366/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 16.26 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | Material Requisition To Resource Division |  |  | RTOR000499/2023-2024 | 4023/BWD | 08/09/2023 |  | Resource Division | 5.83 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | Material Requisition To Resource Division |  |  | RTOR000686/2023-2024 | 5079/BWD | 23/11/2023 |  | Resource Division | 19.78 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | NEW SERVICE CONNECTION FOR PASCHIM NABAGRAM PWSS PH-2 |  |  | BILL/00189/2024-2025 | BP-2024-25-86 | 15/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.13 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | NEW SERVICE CONNECTION FOR PASCHIM NABAGRAM PWSS PH-1 |  |  | BILL/00190/2024-2025 | BP-2024-25-85 | 15/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.06 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | Additional Quotation for service connection at Paschim Nabagram PWSS PH-2. |  |  | BILL/00419/2024-2025 | BP-2024-25-220 | 26/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 31/10/2024 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME | SM/14964 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PASCHIM NABAGRAM Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000926/2023-2024 | 4189/CMD | 29/08/2023 | 28/09/2023 | M/S. S.R. ENTERPRISE | 29.91 | 12 | 40.11 | 43
Total | [13 empty] | 626.56 | 152.48 | 24.34