## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000511/2023-2024 | 3689/BWD | 23/08/2023 | 22/08/2024 | THE MAHADEV CONSTRUCTION | 734.18 | 0 | 0 | 24
2 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | Material Requisition To Resource Division |  |  | RTOR000279/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 18.45 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | Material Requisition To Resource Division |  |  | RTOR000510/2023-2024 | 4034/BWD | 08/09/2023 |  | Resource Division | 3.06 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali - I | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | Material Requisition To Resource Division |  |  | RTOR000808/2023-2024 | 299/BWD | 24/01/2024 |  | Resource Division | 14.63 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | Additional Quotation for new service connection for Sahapur PWSS, PH-1. |  |  | BILL/00311/2024-2025 | BP-2024-25-152 | 21/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.86 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | New service connection charges for Sahapur PWSS TW-2 |  |  | BILL/01831/2023-2024 | BP-2023-24-337 | 06/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.21 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | New service connection for Sahapur PWSS. |  |  | BILL/02249/2023-2024 | BP-2023-24-389 | 17/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.86 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SAHAPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000036/2023-2024 | 2473/CMD | 30/05/2023 | 29/06/2023 | MAA KALI ENTERPRISE | 20.8 | 7.02 | 33.76 | 60
9 | PURBA BARDHAMAN | Purbasthali - I | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME | SM/14969 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 0
Total | [13 empty] | 858.66 | 7.02 | 0.82