## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME | SM/14973 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000477/2023-2024 | 3491/BWD | 09/08/2023 | 08/08/2024 | POWER TOOLS & ENGINEERING | 1741.05 | 0 | 0 | 10
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME | SM/14973 | New | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001080/2023-2024 | 22/KTS | 05/01/2024 | 15/03/2024 | AJIT SAMANTA | 0.9 | 0 | 0 | 100
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME | SM/14973 | New | Material Requisition To Resource Division |  |  | RTOR000242/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 7.44 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME | SM/14973 | New | Material Requisition To Resource Division |  |  | RTOR000457/2023-2024 | 3981/BWD | 08/09/2023 |  | Resource Division | 44.04 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME | SM/14973 | New | Material Requisition To Resource Division |  |  | RTOR000665/2023-2024 | 5086/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | DEULIA PIPED WATER SUPPLY SCHEME | SM/14973 | New | QUOTATION FOR NEW SERVICE CONNECTION AT DEULIA PWSS TW-1 |  |  | BILL/00368/2024-2025 | BP-2024-25-189 | 08/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.69 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | DEULIA PIPED WATER SUPPLY SCHEME | SM/14973 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | DEULIA PIPED WATER SUPPLY SCHEME | SM/14973 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DEULIA Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000821/2023-2024 | 4098/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 28.94 | 0 | 0 | 0
Total | [13 empty] | 1909.58 | 0 | 0