## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000289/2024-2025 | 2739/BWD | 12/07/2024 | 09/11/2024 | PUSPA ENTERPRISE | 185.75 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000435/2023-2024 | 3387/BWD | 03/08/2023 | 02/08/2024 | PUSPA ENTERPRISE | 1333.98 | 100.69 | 7.55 | 40
3 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 1.83 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Material Requisition To Resource Division |  |  | RTOR000338/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 7.73 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Material Requisition To Resource Division |  |  | RTOR000743/2023-2024 | 5259/BWD | 30/11/2023 |  | Resource Division | 20.18 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Quotation for new service connection at Malgram PWSS PH-I. |  |  | BILL/00346/2024-2025 | BP-2024-25-168 | 01/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.14 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Quotation for new service connection at Malgram PWSS PH-2. |  |  | BILL/00418/2024-2025 | BP-2024-25-225 | 26/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.27 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | MALGRAM PIPED WATER SUPPLY SCHEME | SM/15150 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MALGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000865/2023-2024 | 4120/CMD | 29/08/2023 | 28/09/2023 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 27.75 | 0 | 0 | 0
Total | [13 empty] | 1666.92 | 100.69 | 6.04