## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000288/2024-2025 | 2741/BWD | 12/07/2024 | 09/11/2024 | M/S M.M. ENTERPRISE | 205.15 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | KHATUNDI Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ketugram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000413/2023-2024 | 3258/BWD | 27/07/2023 | 22/05/2024 | SUJAN KUMAR MISTRY | 260.06 | 116.75 | 44.89 | 60
3 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | Material Requisition To Resource Division |  |  | RTOR000384/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 10.05 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | Material Requisition To Resource Division |  |  | RTOR000456/2023-2024 | 3980/BWD | 08/09/2023 |  | Resource Division | 0.66 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | Material Requisition To Resource Division |  |  | RTOR000739/2023-2024 | 5251/BWD | 30/11/2023 |  | Resource Division | 20.18 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | New service connection charges for Khatundi PWSS TW-1 |  |  | BILL/01725/2023-2024 | BP-2023-24-252 | 07/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.23 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | New Service connection for Khatundi PWSS TW-2 |  |  | BILL/02346/2023-2024 | BP-2023-24-463 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.33 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KHATUNDI Water Supply Scheme [Block - KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000848/2023-2024 | 4121/CMD | 29/08/2023 | 28/09/2023 | A.K SIKDAR | 20.81 | 9.27 | 44.53 | 91
10 | PURBA BARDHAMAN | Ketugram - I | Central Drilling | KHATUNDI PIPED WATER SUPPLY SCHEME | SM/15154 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Khatundi W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000172/2023-2024 | 1055/CDD | 16/08/2023 | 15/09/2023 | OSMAN SEKH | 16.61 | 0 | 0 | 0
Total | [13 empty] | 622.36 | 126.02 | 20.25