## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Ankhona, Pandugram, Sripur PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000286/2024-2025 | 2738/BWD | 12/07/2024 | 09/11/2024 | PUSPA ENTERPRISE | 128.29 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANKHONA, PANDUGRAM & SRIPUR Piped Water Supply Scheme under KETUGRAM¿I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000436/2023-2024 | 3388/BWD | 03/08/2023 | 02/08/2024 | PUSPA ENTERPRISE | 989.13 | 57.48 | 5.81 | 50
3 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 1.55 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | Material Requisition To Resource Division |  |  | RTOR000325/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 9.91 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram - I | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | Material Requisition To Resource Division |  |  | RTOR000614/2023-2024 | 4916/BWD | 10/11/2023 |  | Resource Division | 19.75 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | NEW SERVICE CONNECTION FOR SRIPUR PWSS PH-2. |  |  | BILL/00104/2024-2025 | BP-2024-25-45 | 26/04/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.76 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | New Service connection at Sripur PWSS TW-1 |  |  | BILL/02371/2023-2024 | BP-2023-24-489 | 01/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.49 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | New service connection at Sripur PWSS TW No.2 |  |  | BILL/02373/2023-2024 | BP-2023-24-490 | 01/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.54 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ketugram - I | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SRIPUR Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000862/2023-2024 | 4129/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 27.65 | 10.66 | 38.57 | 0
11 | PURBA BARDHAMAN | Ketugram - I | Central Drilling | SRIPUR PIPE WATER SUPPLY SCHEME | SM/15158 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Sripur Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhaman District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000159/2023-2024 | 860/CDD | 10/07/2023 | 09/08/2023 | OSMAN SEKH | 16.62 | 0 | 0 | 0
Total | [13 empty] | 1281.96 | 68.14 | 5.32