## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Providing laying distrfrrrrribution pipe line at Amtala-Sukantapally due to construction of Road by gp for Nababhat PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000143/2024-2025 | 1031/BSD | 10/06/2024 | 10/07/2024 | SANDIPAN SENGUPTA | 0.96 | 0.46 | 47.6 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Restoration of Road damaged by laying of Pipeline with ballah piling work at different location for NABABHAT Piped Water Supply Scheme, Block- Burdwan -I, within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000282/2024-2025 | 2714/BWD | 11/07/2024 | 09/10/2024 | GENUINE ENGINEERS CO-OP. SOCIETY LTD. | 17.93 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Allied work for Augmentation of NABABHAT PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE,Junior Engineer, Burdwan Sadar Sub-Division | ORD/000432/2023-2024 | 3360/BWD | 02/08/2023 | 01/10/2023 | M/S ANAND CONSTRUCTION | 40.09 | 20.04 | 49.98 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with renovation and modification of administrative office complex building under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000450/2023-2024 | 3400/BWD | 03/08/2023 | 02/09/2023 | SANDIPAN SENGUPTA | 7.78 | 7.76 | 99.81 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Renovation of RWS Office Building with Inside flooring, partition wall etc at Nababhat P.H.E Complex within RWS Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer | ORD/000760/2023-2024 | 4742/BWD | 03/11/2023 | 02/01/2024 | SURATH DEY | 2.86 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Toilet Lavatory Renovation of RWS Office Building with Aluminium Partition and ancillary works at Nababhat P.H.E Complex within RWS Sub-Division under Burdwan Division, PHE Dte. | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Junior Engineer | ORD/000812/2023-2024 | 4862/BWD | 10/11/2023 | 09/01/2024 | SURATH DEY | 2.63 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for NABABHAT its Adjoining Mouza W/S Scheme, Block -Bardhaman-I within Burdwan Sub-Division, PHE Dte. (Mouza- KRISHNAPUR) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000830/2022-2023 | 499/BSD | 21/03/2023 | 05/05/2023 | BHASKAR NANDY | 3.16 | 2.73 | 86.42 | 100
8 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with renovation and modification of administrative office complex building under Burdwan Division PHE Dte. (Part - II). | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | J.E. 1 BURDWAN | ORD/000849/2023-2024 | 5156/BWD | 24/11/2023 | 24/12/2023 | SANDIPAN SENGUPTA | 9.63 | 4.78 | 49.63 | 100
9 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Laying of inter connection between 3rd tube well site (Mouza-Krishnapur) and distribution system for Nababhat PWSS within Bardhaman-I Block , under Burdwan Division, PHE Dte |  |  | ORD/000942/2023-2024 | 2951/BSD | 19/12/2023 | 02/02/2024 | I.S. ENTERPRISE | 2.91 | 1.45 | 49.8 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Retrofitting, repairing, exterior & interior plaster work and improvement of floors of Burdwan Sub-Division office Nababhat Purba Bardhhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000996/2023-2024 | 271/BWD | 16/01/2024 | 16/03/2024 | SANDIPAN SENGUPTA | 10.59 | 0 | 0 | 20
11 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Providing laying distribution pipe line due to Constructioon of road by GP for NABABHAT PWSS under Burdwan-I Block of within Burdwan Sub Division under Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/001190/2023-2024 | 536/BSD | 14/03/2024 | 13/04/2024 | NABAKUMAR DAS | 0.86 | 0.65 | 75.72 | 100
12 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | New service connection charges of Aug. Nababhat W/S Scheme TW-3 |  |  | BILL/00686/2023-2024 | BP-2023-24-31 | 23/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.58 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Supply & Installation of submersible pumping machinery, different electro-mechanical works for Nababhat w/s scheme, T.W. No.-I (Replacement tubewell) and Power Backup arrangement at the office of the Burdwan Division & Durgapur w/s Division including RWS, Purba Bardhaman under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000324/2024-2025 | 2695/CMD | 11/09/2024 | 10/11/2024 | CHOUDHURY ENTERPRISE | 24.83 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) | SM/15166 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of NABABHAT( Part-B)[BURDWAN-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000571/2023-2024 | 3899/CMD | 18/08/2023 | 17/09/2023 | CINZANO | 22.41 | 5.59 | 24.95 | 50
Total | [13 empty] | 149.2 | 43.45 | 29.12