## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa - I | Burdwan Division | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | Balance work for Balance work of OHR, construction Concrete Road, 1st Floor of Office Building, Functional Household Tap Connection, land development, Road restoration etc. of Gopekhanji, Jajigram & Gidhagram PWSS under KATWA -I Block, under Katwa Sub Division under Burdwan Divn, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000503/2024-2025 | 3161/BWD | 22/08/2024 | 20/12/2024 | POWER TOOLS & ENGINEERING | 272.54 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa - I | Burdwan Division | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | GOPKHANJI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000741/2022-2023 | 1134/BWD | 13/03/2023 | 12/03/2024 | POWER TOOLS & ENGINEERING | 482.85 | 140.17 | 29.03 | 74
3 | PURBA BARDHAMAN | Katwa - I | Burdwan Division | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 1962/BWD | 25/04/2023 |  | Resource Division | 37.55 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa - I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | New service connection charges for Gopkhanji W/S Scheme TW-1 |  |  | BILL/00696/2023-2024 | BP-2023-24-39 | 27/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.65 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa - I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | New service connection charges for Gopkhanji PWSS TW-2 |  |  | BILL/00822/2023-2024 | BP-2023-24-100 | 03/08/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa - I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa - I | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME | SM/15171 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOPKHANJI Water Supply Scheme [ Block- KATWA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000127/2023-2024 | 2660/CMD | 16/06/2023 | 16/07/2023 | JYOTY SOLAR POWER. | 26.98 | 10.56 | 39.15 | 100
Total | [13 empty] | 882.6 | 150.74 | 17.08