## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | Extension of CIDF/DI Pipes with specials within command area of Balarampur piped W/S Scheme at Shalim Danga Sabgi Bazar,,Jamalpur Development Block under Burdwan Division,PHE Dte. [2nd Call]. |  |  | ORD/000140/2023-2024 | 789/BSD | 28/04/2023 | 13/05/2023 | GHOSH ENTERPRISE | 0.32 | 0.16 | 50.77 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of BALARAMPUR W/S Scheme under Jamalpur Block within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000202/2023-2024 | 2705/BWD | 08/06/2023 | 08/07/2023 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.26 | 12.64 | 95.37 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | Preparation and Submission of DPR for Augmentation of Balarampur PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | RWS_JAMALPUR | ORD/000393/2023-2024 | 1528/BSD | 17/07/2023 | 01/08/2023 | GEO-SOLUTION | 0.78 | 0.77 | 99.01 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | Construction of switch rooms & Rising main at different TW site for BALARAMPUR Piped Water Supply Scheme under Jamalpur Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000594/2023-2024 | 3769/BWD | 29/08/2023 | 28/10/2023 | SOUMYAVASH DAS | 8.94 | 4.46 | 49.83 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | Construction of (i) Pump House cum chlorine room without sanitary and water supply arrangement at 5th Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/ DEC-17 (Size 3.60 mtr x 3.00 mtr room), (CD) and UPVC Deep Well Screen (RDS), (ii) Interconnection between pump house & delivery line for BALARAMPUR W/S Scheme under Jamalpur Block under Burdwan Division, PHE Dte. | AE(HQs) | Junior Engineer, Burdwan Division | ORD/001054/2023-2024 | 832/BWD | 29/02/2024 | 30/03/2024 | SK KHAIRUL ISLAM | 4.79 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | New service connection charges for Balarampur PWSS TW-4 |  |  | BILL/02213/2023-2024 | BP-2023-24-386 | 16/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.6 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | New Service connection at BALARAMPUR PWSS TW-5. |  |  | BILL/02364/2023-2024 | BP-2023-24-482 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.19 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Balarampur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000082/2023-2024 | 2589/CMD | 07/06/2023 | 07/07/2023 | P.K. ENGINEERING | 22.61 | 5.12 | 22.66 | 50
9 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR | SM/15181 | Augmentation | Procurement of electro-mechanical accessories for Balarampur Water Supply Scheme under JJM under CMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001020/2023-2024 | 531/CMSD | 07/07/2023 | 06/08/2023 | M/S. S.D. CONSTRUCTION | 0.58 | 0.29 | 50 | 100
Total | [13 empty] | 81.07 | 23.44 | 28.91