## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR | SM/15195 | Retrofitting | Sinking of Tube Well, Construction of Pump House, Boundary Wall at 3rd TW Site with Extension of Pipeline & Laying Parallel line and Providing FHTC (Leftout] with allied works for DERIAPUR Piped Water Supply Scheme under Raina-I Block within Burdwan Sub Division under Burdwan Division P.H.E Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000177/2024-2025 | 2270/BWD | 18/06/2024 | 16/10/2024 | ROY CONSTRUCTION | 68.15 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR | SM/15195 | Retrofitting | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 10/11/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR | SM/15195 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Astikpur, Dakhinkul & Balagar of DERIAPUR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000762/2022-2023 | 1296/BWD | 21/03/2023 | 20/05/2023 | T.K. BANERJEE & CO. | 68.81 | 49.68 | 72.2 | 74
Total | [13 empty] | 446.55 | 49.68 | 11.12