## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina - I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Restoration of hard shoulder from 0.00 km to 2.918 km of Sagrai Raina Road (MDR) for laying of water supply pipeline of Gopalpur PWSS under Burdwan Division, PHE Dte. |  |  | BILL/01127/2023-2024 | 1084/JJM | 20/12/2023 |  | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 4.72 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Raina - I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOPALPUR & RASUIKHANDA Piped Water Supply Scheme under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000006/2023-2024 | 1691/BWD | 12/04/2023 | 11/04/2024 | SK ALIM | 1081.52 | 144.94 | 13.4 | 92
3 | PURBA BARDHAMAN | Raina - I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 12.69 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina - I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Material Requisition To Resource Division |  |  | RTOR000482/2023-2024 | 4006/BWD | 08/09/2023 |  | Resource Division | 5.14 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina - I | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Material Requisition To Resource Division |  |  | RTOR000669/2023-2024 | 5083/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina - I | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | New service connection charges for Gopalpur PWSS TW-2 |  |  | BILL/01528/2023-2024 | BP-2023-24-193 | 11/10/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.82 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina - I | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | New electric connection for Gopalpur PWSS. |  |  | BILL/01869/2023-2024 | BP-2023-24-344 | 11/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.66 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina - I | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina - I | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15235 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gopalpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000720/2023-2024 | 4031/CMD | 29/08/2023 | 28/09/2023 | M/S. SWAPAN BANERJEE | 28.98 | 11.39 | 39.29 | 48
Total | [13 empty] | 1235.56 | 156.32 | 12.65