## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | PASHALA PIPED WATER SUPPLY SCHEME | SM/15245 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000739/2023-2024 | 4652/BWD | 31/10/2023 | 30/10/2024 | STARCO CONSTRUCTIONS | 900.17 | 0 | 0 | 2
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | PASHALA PIPED WATER SUPPLY SCHEME | SM/15245 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 0.33 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | PASHALA PIPED WATER SUPPLY SCHEME | SM/15245 | New | Material Requisition To Resource Division |  |  | RTOR000367/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 4.8 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Burdwan Division | PASHALA PIPED WATER SUPPLY SCHEME | SM/15245 | New | Material Requisition To Resource Division |  |  | RTOR000757/2023-2024 | 5242/BWD | 30/11/2023 |  | Resource Division | 18.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | PASHALA PIPED WATER SUPPLY SCHEME | SM/15245 | New | NEW SERVICE CONNECTION FOR PASHALA PWSS |  |  | BILL/02594/2023-2024 | BP-2023-24-550 | 20/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.16 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | PASHALA PIPED WATER SUPPLY SCHEME | SM/15245 | New | NEW SERVICE CONNECTION FOR PASHALA PWSS |  |  | BILL/02595/2023-2024 | BP-2023-24-549 | 20/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 14.97 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Central Mechanical | PASHALA PIPED WATER SUPPLY SCHEME | SM/15245 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Bhatar | Central Mechanical | PASHALA PIPED WATER SUPPLY SCHEME | SM/15245 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PASHALA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000777/2023-2024 | 4071/CMD | 29/08/2023 | 28/09/2023 | SOUNAK ENTERPRISE | 27.79 | 0 | 0 | 0
Total | [13 empty] | 1052.72 | 0 | 0