## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina - II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARABAINAN & CHAUDANGA Piped Water Supply Scheme under Raina ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000412/2023-2024 | 3257/BWD | 27/07/2023 | 26/07/2024 | SK ALIM | 1144.16 | 58.51 | 5.11 | 30
2 | PURBA BARDHAMAN | Raina - II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Material Requisition To Resource Division |  |  | RTOR000303/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 12.3 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina - II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Material Requisition To Resource Division |  |  | RTOR000419/2023-2024 | 3863/BWD | 01/09/2023 |  | Resource Division | 3.95 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina - II | Burdwan Division | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Material Requisition To Resource Division |  |  | RTOR000662/2023-2024 | 5082/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina - II | Central Mechanical | Chaudanga Piped Water Supply Scheme | SM/15489 | New | New electric connection for Chaudanga PWSS, PH-1. |  |  | BILL/01884/2023-2024 | BP-2023-24-347 | 11/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.67 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina - II | Central Mechanical | Chaudanga Piped Water Supply Scheme | SM/15489 | New | New electric connection for Chuadanga PWSS, PH-2. |  |  | BILL/01885/2023-2024 | BP-2023-24-348 | 11/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina - II | Central Mechanical | Chaudanga Piped Water Supply Scheme | SM/15489 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAUDANGA Water Supply Scheme [ Block-RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000805/2023-2024 | 4090/CMD | 29/08/2023 | 28/09/2023 | MS DAS ELECTRIC CO | 28.98 | 5.76 | 19.89 | 0
Total | [13 empty] | 1216.65 | 64.28 | 5.28