## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I | SM/15571 | Augmentation | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 18/10/2024 | M/S DATTA ENTERPRISE | 579.85 | 0 | 0 | 2
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I | SM/15571 | Augmentation | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-1A) with LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site including laying of Rising Main from Kamalnagar WTP to additional OHR and interconnection Old & New OHR under Purbasthali-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000426/2023-2024 | 3329/BWD | 02/08/2023 | 01/08/2024 | MANASH GHOSH | 513.64 | 163.61 | 31.85 | 20
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I | SM/15571 | Augmentation | Work order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-I (Zone-1A) (SM/15571) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-6) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001139/2023-2024 | 2081/KSD | 29/02/2024 | 14/04/2024 | APEX ENGINEERING | 2.23 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I | SM/15571 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000516/2023-2024 | 3970/BWD | 08/09/2023 |  | Resource Division | 18.33 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I | SM/15571 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000761/2023-2024 | 202/BWD | 10/01/2024 |  | Resource Division | 6.16 | 0 | 0 | 0
Total | [13 empty] | 1120.21 | 163.61 | 14.61