## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 |  |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I |  |  | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000181/2024-2025 | 2296/BWD | 20/06/2024 | 26/02/2026 | M/S DATTA ENTERPRISE | 579.85 | 0 | 0 | 2
2 |  |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I |  |  | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-1A) with LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site including laying of Rising Main from Kamalnagar WTP to additional OHR and interconnection Old & New OHR under Purbasthali-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000426/2023-2024 | 3329/BWD | 02/08/2023 | 29/03/2026 | MANASH GHOSH | 513.64 | 264.77 | 51.55 | 20
3 |  |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I |  |  | Work order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-I (Zone-1A) (SM/15571) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-6) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001139/2023-2024 | 2081/KSD | 29/02/2024 | 14/04/2024 | APEX ENGINEERING | 2.23 | 0 | 0 | 100
4 |  |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I |  |  | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
5 |  |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I |  |  | Material Requisition To Resource Division |  |  | RTOR000516/2023-2024 | 3970/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 18.33 | 0 | 0 | 0
6 |  |  | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I |  |  | Material Requisition To Resource Division |  |  | RTOR000761/2023-2024 | 202/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 6.16 | 0 | 0 | 0
7 |  |  | Central Mechanical | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I |  |  | Quotation for meter shifting at Purbasthali PWSS PH 1. |  |  | BILL/00935/2024-2025 | BP-2024-25-409 | 11/12/2024 | 11/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.05 | 0 | 0 | 0
8 |  |  | Central Mechanical | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I |  |  | Supply and installation of disinfection arrangement (Gaseous Chlorination) and other works at different OHR sites of Aug. of Purbasthali Surface Water Based PWSS Zone-I under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000008/2025-2026 | 1031/CMD | 25/04/2025 | 25/05/2025 | EASTERN INDIA SALES & SERVICE | 147.66 | 0 | 0 | 0
Total | [13 empty] | 2477.54 | 264.77 | 10.69