## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15583 | New | GOPALPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Jamalpur Block, District:- Purba-Bardhaman [NEW SCHEME] | AE(HQs) | Junior Engineer, Burdwan Division | ORD/000121/2023-2024 | 2305/BWD | 19/05/2023 | 16/09/2023 | IJABUL SEKH | 266.75 | 41.52 | 15.57 | 40
2 | PURBA BARDHAMAN | Jamalpur | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15583 | New | Material Requisition To Resource Division |  |  | RTOR000268/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 17.02 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15583 | New | New service connection for Gopalpur PWSS TW-1. |  |  | BILL/02282/2023-2024 | BP-2023-24-433 | 29/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15583 | New | New Service connection at GOPALPUR PWSS TW-2. |  |  | BILL/02363/2023-2024 | BP-2023-24-483 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.65 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Jamalpur | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME | SM/15583 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at GOPALPUR Water Supply Scheme [Block-JAMALPUR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000904/2023-2024 | 4168/CMD | 29/08/2023 | 28/09/2023 | SOUNAK ENTERPRISE | 22.1 | 0 | 0 | 0
Total | [13 empty] | 323.52 | 41.52 | 12.83