## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | SM/15722 | Augmentation | Preparation and Submission of DPR for Augmentation of Gobindapur PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000366/2023-2024 | 1529/BSD | 17/07/2023 | 01/08/2023 | CARTO | 0.78 | 0.38 | 49.51 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | SM/15722 | Augmentation | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 10/11/2024 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | SM/15722 | Augmentation | Extension of PVC water supply line for GOBINDAPUR and its adjoining Mouza W/S Scheme, Block-Memari-I within Burdwan Sub-Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, RWS, Memari-I Dev. Bolck | ORD/000623/2023-2024 | 3920/BWD | 05/09/2023 | 05/10/2023 | J K CORPORATION | 27.92 | 11.78 | 42.19 | 98
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR | SM/15722 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 at Augmentation of GOBINDAPUR Water Supply Scheme [BLOCK- MEMARI-I] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001610/2023-2024 | 1538/CMD | 05/03/2024 | 04/05/2024 | BEHERA ENTERPRISE | 12.33 | 0 | 0 | 0
Total | [13 empty] | 350.62 | 12.16 | 3.47