## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | SM/15753 | Augmentation | Providing 20 Nos.FHTC at AMAR & KAMODPUR village for declearation of SWAJALGRAM under NATUNGRAM Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000145/2024-2025 | 1034/BSD | 10/06/2024 | 10/07/2024 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.94 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | SM/15753 | Augmentation | Preparation and Submission of DPR for Augmentation of Natungram PWSS under Burdwan-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000347/2023-2024 | 1474/BSD | 12/07/2023 | 27/07/2023 | MEASURE LAND | 0.78 | 0.77 | 99.01 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM | SM/15753 | Augmentation | Augmentation of NATUNGRAM Piped Water Supply Scheme Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & Rising Main under BARDHAMAN-I Block, District:- Purba-Bardhaman. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000579/2023-2024 | 3726/BWD | 25/08/2023 | 24/08/2024 | BASU ENTERPRISE | 72.82 | 18.88 | 25.93 | 40
Total | [13 empty] | 74.53 | 19.65 | 26.36