## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME | SM/16016 | Augmentation | Augmentation of KSHETPUR PALASHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & Renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000117/2023-2024 | 2303/BWD | 19/05/2023 | 16/09/2023 | SHUBHRA KANTI GHOSH | 121.71 | 46.04 | 37.83 | 95
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME | SM/16016 | Augmentation | New service connection charges for Kshetpur Palashi PWSS TW-1 |  |  | BILL/01764/2023-2024 | BP-2023-24-280 | 21/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME | SM/16016 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Kshetpur Plasi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000094/2023-2024 | 2585/CMD | 07/06/2023 | 07/07/2023 | SOUNAK ENTERPRISE | 22.6 | 5.14 | 22.76 | 48
Total | [13 empty] | 148.31 | 51.19 | 34.51