## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | Different types of works involve in connection with Augmentation of KALYANPUR (SM/16299) Water Supply Scheme & BHABANANDAPUR (SM/16024) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER RWS KALNA2 | ORD/000189/2024-2025 | 2433/BWD | 27/06/2024 | 25/10/2024 | BALAJEE ENTERPRISES | 225.16 | 0 | 0 | 2
2 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANGARSON, BHABANANDAPUR &DAFARPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000702/2023-2024 | 4480/BWD | 11/10/2023 | 10/10/2024 | M/S GHOSH & CO. | 1093.29 | 0 | 0 | 35
3 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 44.37 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | Material Requisition To Resource Division |  |  | RTOR000251/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 18.56 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | Quotation for new service connection for Bhabanandapur PWSS PH-2. |  |  | BILL/00284/2024-2025 | BP-2024-25-144 | 11/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.78 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | Additional quotation for Bhavanandapur PWSS PH-1 |  |  | BILL/00427/2024-2025 | BP-2024-25-223 | 26/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.67 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | New service connection for BHABANANDAPUR PWSS TW-1. |  |  | BILL/02394/2023-2024 | BP-2023-24-500 | 06/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.85 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000116/2024-2025 | 2393/CMD | 02/08/2024 | 31/10/2024 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME | SM/16024 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHABANANDAPUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000922/2023-2024 | 4161/CMD | 29/08/2023 | 28/09/2023 | SOUNAK ENTERPRISE | 28.48 | 0 | 0 | 0
Total | [13 empty] | 1498.97 | 0 | 0