## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection Vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.06.2024 to 30.11.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000465/2024-2025 | 272/KSD | 30/05/2024 | 29/11/2024 | PARTHA PRATIM ACHARYA | 2.4 | 1.22 | 50.91 | 0
2 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANGARSON, BHABANANDAPUR &DAFARPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000702/2023-2024 | 4480/BWD | 11/10/2023 | 10/10/2024 | M/S GHOSH & CO. | 1093.29 | 0 | 0 | 35
3 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000983/2023-2024 | 1681/KSD | 22/11/2023 | 23/05/2024 | PARTHA PRATIM ACHARYA | 0.87 | 1.24 | 143.21 | 51
4 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DAFARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001148/2023-2024 | 2104/KSD | 04/03/2024 | 14/03/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 99.78 | 2
5 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024]" (Vehicle No-WB 04G 7127) | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001248/2023-2024 | 1681/KSD | 22/11/2023 | 23/05/2024 | PARTHA PRATIM ACHARYA | 2.4 | 0.31 | 12.79 | 0
6 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 28.1 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna - II | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Material Requisition To Resource Division |  |  | RTOR000237/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 12.02 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Additional quotation for Dafarpur PWSS PH-2 |  |  | BILL/00426/2024-2025 | BP-2024-25-224 | 26/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | New service at Dafarpur PWSS TW-2. |  |  | BILL/02292/2023-2024 | BP-2023-24-438 | 29/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | NEW SERVICE CONNECTION FOR DAFARPUR PWSS TW -1. |  |  | BILL/03103/2023-2024 | BP-2023-24-643 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 20.65 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Kalna - II | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME | SM/16028 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at DAFARPUR Water Supply Scheme [Block - KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000895/2023-2024 | 4158/CMD | 29/08/2023 | 28/09/2023 | GOENKA ENTERPRISE | 20.81 | 0 | 0 | 0
Total | [13 empty] | 1189.41 | 3.43 | 0.29