## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME | SM/16196 | Augmentation | Augmentation of BUNDEBAJ PWSS to accommodate FHTC Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000728/2023-2024 | 4615/BWD | 17/10/2023 | 16/12/2023 | M/S CHANDRANATH MUKHERJEE | 39.76 | 16.74 | 42.1 | 100
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME | SM/16196 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BUNDEBAJ[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/001078/2023-2024 | 4202/CMD | 29/08/2023 | 28/09/2023 | C.M. ENTERPRISE | 24.42 | 0 | 0 | 0
Total | [13 empty] | 64.18 | 16.74 | 26.08