## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000388/2023-2024 | 3197/BWD | 24/07/2023 | 23/07/2024 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 0 | 0 | 30
2 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Material Requisition To Resource Division |  |  | RTOR000314/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 5.01 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Material Requisition To Resource Division |  |  | RTOR000480/2023-2024 | 4004/BWD | 08/09/2023 |  | Resource Division | 7.71 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Material Requisition To Resource Division |  |  | RTOR000693/2023-2024 | 5072/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina - I | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | New service connection charges for Shukur PWSS TW-2 |  |  | BILL/01762/2023-2024 | BP-2023-24-272 | 15/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.71 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina - I | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | New Service connection for Sukur W/S Scheme PH No.-I |  |  | BILL/01793/2023-2024 | BP-2023-24-318 | 30/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.06 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina - I | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME | SM/16255 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shukur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000724/2023-2024 | 4035/CMD | 29/08/2023 | 28/09/2023 | S.P. CONSTRUCTION | 28.98 | 0 | 0 | 0
Total | [13 empty] | 1314.96 | 0 | 0