## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa - I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | BAINCHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,Junior Engineer, R.W.S., Katwa-I Dev. Block | ORD/000486/2023-2024 | 3503/BWD | 10/08/2023 | 09/08/2024 | MAA ENGINEERS CO. OPERATIVE & CONSTRUCTION SOCIETY LTD. | 521.7 | 44.5 | 8.53 | 5
2 | PURBA BARDHAMAN | Katwa - I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 13.1 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa - I | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Material Requisition To Resource Division |  |  | RTOR000506/2023-2024 | 4030/BWD | 08/09/2023 |  | Resource Division | 46.22 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa - I | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000069/2024-2025 | 2399/CMD | 02/08/2024 | 31/10/2024 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa - I | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME | SM/18335 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAINCHI Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000885/2023-2024 | 4148/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 30.35 | 0 | 0 | 0
Total | [13 empty] | 666.53 | 44.5 | 6.68