## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | Restoration work of Sankarpur - Nibhuji bazar Road from 13.80 km to 15.75km. damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under Kalna Highway sub Division of Burdwan south Highway Division P.W(Roads) Dte . During the year 2023-24 |  |  | BILL/00644/2024-2025 | null | 10/09/2024 |  | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 3.34 | 0 | 0 | null
2 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELSHAR & SANKARPUR Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000411/2023-2024 | 3256/BWD | 27/07/2023 | 26/07/2024 | SK ALIM | 1345.74 | 145.68 | 10.83 | 44
3 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | Material Requisition To Resource Division |  |  | RTOR000280/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 6.97 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | Material Requisition To Resource Division |  |  | RTOR000427/2023-2024 | 3858/BWD | 01/09/2023 |  | Resource Division | 2.13 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Raina - I | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | Material Requisition To Resource Division |  |  | RTOR000691/2023-2024 | 5066/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Raina - I | Central Mechanical | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | New service connection for Shankarpur PWSS TW-1. |  |  | BILL/02279/2023-2024 | BP-2023-24-436 | 29/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.32 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Raina - I | Central Mechanical | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | NEW SERVICE CONNECTION FOR SANKARPUR PWSS TW 2. |  |  | BILL/03181/2023-2024 | BP-2023-24-665 | 22/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.26 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Raina - I | Central Mechanical | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000117/2024-2025 | 2589/CMD | 27/08/2024 | 25/11/2024 | DEY ENTERPRISE | 74.58 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Raina - I | Central Mechanical | SANKARPUR PIPED WATER SUPPLY SCHEME | SM/18337 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sankarpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000723/2023-2024 | 4034/CMD | 29/08/2023 | 28/09/2023 | GOENKA ENTERPRISE | 29.4 | 11.69 | 39.75 | 95
Total | [13 empty] | 1489.19 | 157.37 | 10.57