## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME | SM/18343 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000107/2024-2025 | 485/KTS | 16/04/2024 | 27/06/2024 | AJIT SAMANTA | 0.92 | 0.21 | 22.22 | 10
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME | SM/18343 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | J.E. katwa,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000461/2023-2024 | 3443/BWD | 08/08/2023 | 07/08/2024 | ASHOK KUMAR GHOSH | 1588.1 | 0 | 0 | 15
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME | SM/18343 | New | Material Requisition To Resource Division |  |  | RTOR000274/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 16.69 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME | SM/18343 | New | Material Requisition To Resource Division |  |  | RTOR000408/2023-2024 | 3872/BWD | 01/09/2023 |  | Resource Division | 1.27 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME | SM/18343 | New | Material Requisition To Resource Division |  |  | RTOR000571/2023-2024 | 4921/BWD | 10/11/2023 |  | Resource Division | 27.49 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | HALIMPUR PIPE WATER SUPPLY SCHEME | SM/18343 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | HALIMPUR PIPE WATER SUPPLY SCHEME | SM/18343 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at HALIMPUR Water Supply Scheme [ Block- MANGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000871/2023-2024 | 4134/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 45.29 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Drilling | HALIMPUR PIPE WATER SUPPLY SCHEME | SM/18343 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Halimpur W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2023-2024 | 1340/CDD | 13/09/2023 | 01/09/2024 | M/S SAIKAT ENTERPRISE | 23.35 | 5.4 | 23.12 | 50
Total | [13 empty] | 1765.17 | 5.6 | 0.32