## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENUA, IBRAMBAD & UJNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000462/2023-2024 | 3456/BWD | 08/08/2023 | 07/08/2024 | M/S S. CHOUDHURY | 2123.7 | 0 | 0 | 20
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | Material Requisition To Resource Division |  |  | RTOR000333/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 19.69 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | Material Requisition To Resource Division |  |  | RTOR000794/2023-2024 | 316/BWD | 24/01/2024 |  | Resource Division | 47.08 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION FOR UJNA PWSS PH-3 |  |  | BILL/00187/2024-2025 | BP-2024-25-88 | 15/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.3 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | New service connection charges for Ujna PWSS TW-2 |  |  | BILL/01708/2023-2024 | BP-2023-24-235 | 06/12/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.34 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | New service connection charges for Ujna PWSS TW-1 |  |  | BILL/02199/2023-2024 | BP-2023-24-406 | 17/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.99 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | New service connection charges for Ujna PWSS TW-3 |  |  | BILL/02200/2023-2024 | BP-2023-24-406 | 17/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2024 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Manteswar | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/18422 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at UJNA Water Supply Scheme [ Block- MONTESWAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000781/2023-2024 | 4074/CMD | 29/08/2023 | 28/09/2023 | CONCORD ENGINEERING | 44.42 | 21.22 | 47.76 | 90
Total | [13 empty] | 2327.29 | 21.22 | 0.91