## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa - II | Burdwan Division | AMUL PIPED WATER SUPPLY SCHEME | SM/18458 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMUL & AURIA Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000389/2023-2024 | 3198/BWD | 24/07/2023 | 23/07/2024 | MANASH GHOSH | 1418.89 | 0 | 0 | 48
2 | PURBA BARDHAMAN | Katwa - II | Burdwan Division | AMUL PIPED WATER SUPPLY SCHEME | SM/18458 | New | Material Requisition To Resource Division |  |  | RTOR000209/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 4.61 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa - II | Burdwan Division | AMUL PIPED WATER SUPPLY SCHEME | SM/18458 | New | Material Requisition To Resource Division |  |  | RTOR000435/2023-2024 | 3851/BWD | 01/09/2023 |  | Resource Division | 43.58 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME | SM/18458 | New | Quotation for new service connection at Amul PWSS PH-3 |  |  | BILL/00386/2024-2025 | BP-2024-25-207 | 18/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME | SM/18458 | New | New Service connection for Amul PWSS TW-1 |  |  | BILL/02347/2023-2024 | BP-2023-24-464 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME | SM/18458 | New | New Service connection for Amul PWSS TW-2 |  |  | BILL/02348/2023-2024 | BP-2023-24-465 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.77 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME | SM/18458 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa - II | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME | SM/18458 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at AMUL Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000795/2023-2024 | 4083/CMD | 29/08/2023 | 28/09/2023 | JAL PRAVAHIKA PVT LTD | 44.4 | 5.87 | 13.22 | 0
Total | [13 empty] | 1571.01 | 5.87 | 0.37