## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari - I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000557/2024-2025 | 1500/BSD | 30/07/2024 | 04/10/2024 | PARVIN BEGAM | 0.85 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari - I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHANCHAL & NUDIPUR Piped Water Supply Scheme under Memari I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000692/2023-2024 | 4389/BWD | 05/10/2023 | 04/10/2024 | MANASH GHOSH | 1343.97 | 0 | 0 | 20
3 | PURBA BARDHAMAN | Memari - I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Material Requisition To Resource Division |  |  | RTOR000358/2023-2024 | 2197/BWD | 12/05/2023 |  | Resource Division | 19.77 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari - I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Material Requisition To Resource Division |  |  | RTOR000533/2023-2024 | 4295/BWD | 29/09/2023 |  | Resource Division | 3.92 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari - I | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Material Requisition To Resource Division |  |  | RTOR000684/2023-2024 | 5057/BWD | 23/11/2023 |  | Resource Division | 20.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari - I | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | New service connection at Nudipur PWSS PH-2 |  |  | BILL/02354/2023-2024 | BP-2023-24-468 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.43 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari - I | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | New service connection at Nudipur PWSS PH-1 |  |  | BILL/02356/2023-2024 | BP-2023-24-467 | 31/01/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.67 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari - I | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000100/2024-2025 | 2392/CMD | 02/08/2024 | 31/10/2024 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari - I | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME | SM/18834 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nudipur Water Supply Scheme [ Block- Memari-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001092/2023-2024 | 4512/CMD | 06/10/2023 | 05/11/2023 | JAL PRAVAHIKA PVT LTD | 28.96 | 0 | 0 | 0
Total | [13 empty] | 1483.64 | 0 | 0