## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Repairing of existing structure of WTP and it's different units and other allied works under Zone-I (Fatepur) & Zone-II (Hapania) under Surface Based PWSS for Harinnghata & Chakdah (Part) under JJM under Zone-I & Zone-II, Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl.10 | Assistant Engineer-I | Junior Engineer-II | ORD/000033/2023-2024 | 998 /NAD-I | 17/04/2023 | 12/05/2023 | SUMAN CHAKRABORTY | 45.59 | 45.49 | 99.79 | 0
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Jackpushing of Clear Water Rising Main at Kalyani More Crossing at NH-34 and other allied works under Jal Jeevan Mission (JJM) for Zone-I Fatepur at Haringhta Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme for Zone-I, (Fatepur), Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000035/2023-2024 | 1283 /NAD-I | 08/05/2023 | 07/06/2023 | GBC INFRASTRUCTURE PRIVATE LIMITED | 55.87 | 55.81 | 99.89 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Augmentation work at Bhabanipur Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000058/2023-2024 | 268/AE-I/NAD-I | 05/06/2023 | 12/06/2023 | MALI CONSTRUCTION | 0.9 | 0.9 | 99.83 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Augmentation work at Satyapole Mouza under JJM in connection with Augmenation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000059/2023-2024 | 269/AE-I/NAD-I | 05/06/2023 | 12/06/2023 | M/S ARATI ENTERPRISE | 0.89 | 0.89 | 99.83 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Augmentation work at Panchkahania Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000060/2023-2024 | 266/AE-I/NAD-I | 05/06/2023 | 12/06/2023 | M/S ARATI ENTERPRISE | 0.93 | 0.93 | 100 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Augmentation work at Behara Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000061/2023-2024 | 267/AE-I/NAD-I | 05/06/2023 | 12/06/2023 | MALI CONSTRUCTION | 0.91 | 0.91 | 100 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Fatepur ZoneI under Surface WS Scheme of Haringhata Chakdah Part under NAD I PHE Dte (Sl.no.05) | Assistant Engineer-I | Junior Engineer-II | ORD/000081/2022-2023 | 1817/ NAD-I | 26/09/2022 | 25/11/2022 | SHYAMAL SHIL | 25.68 | 25.11 | 97.76 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Repair of 1100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Hapania Zone-II under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte.(Sl. No. 04) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000153/2022-2023 | 3447/NAD-I | 21/12/2022 | 04/02/2023 | B.S. ENTERPRISE | 37.53 | 37.46 | 99.82 | 100
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II (Hapania) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-I | Junior Engineer-II | ORD/000156/2021-2022 | 423/NAD-I | 07/03/2022 | 06/05/2022 | SUMAN CHAKRABORTY | 85.3 | 80.85 | 94.78 | 100
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-I (Fatepur) at Haringhta Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-I, Fatepur,Part-III under Nadia Arsenic Division-I, PHE Dte. (sl.no.15) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000163/2022-2023 | 3515 / NAD-I | 09/01/2023 | 10/03/2023 | MALI CONSTRUCTION | 97.06 | 88.42 | 91.09 | 70
11 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Repairing of existing structure of WTP and other alliedworks under Zone-I (Fatepur) & Zone-II (Hapania)under Surface Water Based PWSS for Haringhata&Chakdah(Part) under Zone-I (Fatepur) & Zone-II(Hapania), Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (sl.11) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000211/2022-2023 | 200 / NAD-I | 15/02/2023 | 16/04/2023 | SUMAN CHAKRABORTY | 63.13 | 62.91 | 99.65 | 55
12 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Augmentation work for Zone-I (Fatepur) G.P. at Haringhata Block under Jal Jeevna Mission (JJM) by Augmentation of Surface Water Based PWSS forHaringhata & Chakdah (Part) for Zone-I (Fatepur) Part-III under Nadia Arsenic Division-I, PHE Dte. (SL.09) | Assistant Engineer-I | Junior Engineer-I | ORD/000219/2022-2023 | 259/NAD-I | 20/02/2023 | 21/04/2023 | BKB INFRA PROJECTS PRIVATE LIMITED | 40.51 | 17.23 | 42.54 | 100
13 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone -I, (Fatepur) and Zone- II (Hapania), Part-III at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/09968 | Augmentation | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II , Hapania at Nagarukhra G.P at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-II, Hapania, Part-III under Nadia Arsenic Division-I, PHE Dte. (sl. 18) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000221/2022-2023 | 303 /NAD-I | 27/02/2023 | 28/04/2023 | MONDAL ENTERPRISE | 96.62 | 59.47 | 61.55 | 74
Total | [13 empty] | 550.92 | 476.38 | 86.47