## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Interconnection between node point 1 to node point 105 in connection with augmentation work at Priyanagar under Zone-XI, Chanduria W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte.(SL.11) | Assistant Engineer-II | Junior Engineer-I,Junior Engineer-III | ORD/000010/2023-2024 | 535 /NAD-I | 13/04/2023 | 04/05/2023 | ABDUL ALIM MONDAL | 33.72 | 33.72 | 100 | 0
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Laying of rising main and distribution pipeline in revised alignment along NH-34 for Simurali (Zone-X), Chanduria (Zone-XII), Joykrishnapur (Zone-II) in connection with providing FHTC for Simurali(Zone-X), Chanduria (Zone-XII), Joykrishnapur (Zone-II) under JJM by Augmentation of Surface Water Based PWSS for Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, P.H.E.Dte. (sl.01) | Assistant Engineer-I | Junior Engineer-II | ORD/000030/2023-2024 | 1254/ NAD-I | 04/05/2023 | 25/05/2023 | BUDDHADEV MONDAL | 42.85 | 42.82 | 99.93 | 0
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Jack Pushing of Clearwater Rising Main Pipeline at Chakdah Chowmataha Crossing along NH-12 and other allied works under Jal Jeevan Mission (JJM) for Joykrishnapur (Zone-II), Chanduria (Zone-XI), Simurali (Zone-X), Ghetugachi (Zone-IX), Baraberia (Zone-VIII), Rukminidanga (Zone-IV) at Chakdah Block under Surface Water based PWSS for Chakdah Water Supply Scheme in connection with Providing FHTC for Joykrishnapur (Zone-II), Chanduria (Zone-XI), Simurali (Zone-X), Ghetugachi (Zone-IX), Baraberia (Zone-VIII), Rukminidanga (Zone-IV) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.13) | Assistant Engineer-II | Junior Engineer-IV | ORD/000036/2023-2024 | 1276 / NAD-I | 08/05/2023 | 29/05/2023 | GBC INFRASTRUCTURE PRIVATE LIMITED | 58.64 | 58.53 | 99.8 | 0
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Simurali Zone-XI under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no. 06) | Assistant Engineer-II | Junior Engineer-III,Junior Engineer-IV | ORD/000054/2022-2023 | 1433 / NAD-I | 16/08/2022 | 30/09/2022 | ONKAR ENTERPRISE | 29.88 | 29.51 | 98.76 | 100
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Retrofitting work at Sanyalchar bablatala to Sanyalchar High School under Chanduria(Zone-XI) W/S Scheme in connection with augmentation of Chanduria W/S Scheme under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E Dte (sl.no.06) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-III | ORD/000057/2023-2024 | 1459/NAD-I | 29/05/2023 | 19/06/2023 | SHYAMAL SHIL | 13.29 | 12.42 | 93.46 | 100
6 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Interconnection from Node point 178 to node point 188 for Augmentation work at Tetulberia, Khorgachi,mollabelia village under Joykrishna ( Zone- II ) Water supply scheme under Jal Jeevan Mission for Chakdah Water bsaed PWSS within Chakdah Block ( Part ) under Nadia Arsenic Division-I, PHE Dte.(SL.07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000069/2023-2024 | 1383/NAD-I | 16/05/2023 | 06/06/2023 | M/S A.K. CONSTRUCTION | 25.14 | 20.15 | 80.17 | 100
7 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Retrofitting work at Tangra & Bagdob for augmentation of Surface water based PWSS for providing FHTC at Purba Bishnupur ( Zone V) of Surfac water based piped water supply scheme for Chakdah ( Part ) under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (SL.No.11) | Assistant Engineer-II | Junior Engineer-IV | ORD/000076/2023-2024 | 1400/NAD-I | 16/05/2023 | 10/06/2023 | CHANDAN ROY | 47.15 | 0.79 | 1.68 | 100
8 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Interconnection between node point 3 and 76 of Balagarichar W/S Scheme for augmentation work at Uttar Ghughia village under Chakdah (Part) Water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000079/2023-2024 | 1412/NAD-I | 18/05/2023 | 17/06/2023 | MESSRS FREEDOM CONSTRUCTION | 62.36 | 9.39 | 15.05 | 100
9 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Construction of Boundary wall and pathway and Room at Head work site of Joykrishnapur OHR Site (Zone-II), Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Jeeva Mission for Zone-II (Joykrishnapur) Part-II, Providing FHTC under Jal Jeevan Mission (JJM) Zone -VIII (Barberia) Part-IV, Providing FHTC under Jal Jeevan Mission (JJM) Zone-X (Simurali) Part-IV and Providing FHTC under Jal Jeevan Mission (JJM) Zone-IV (Rukminidanga) Part-III at Chakdah Block by Augmentation of Surface Water Based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000106/2023-2024 | 1709/NAD-I | 14/07/2023 | 12/10/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 608.25 | 154.59 | 25.42 | 75
10 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Retrofitting work Kajir baganunder Chanduria (Zone-XI) W/S Scheme in connection with augmentation of Chanduria W/S Scheme under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000149/2023-2024 | 377/AE-II/NAD-I | 29/08/2023 | 05/09/2023 | ASHIM ENTERPRISE | 1.17 | 0.41 | 35.53 | 100
11 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Construction of Pathway from Madnapur PWD road to Tantipara and allied works in connection with Augmentation of Surface Water Based W/S Scheme for Arsenic affected areas of Chakdah (Part Block) of Nadia district Zone-X (Chanduria) under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000150/2023-2024 | 378/AE-II/NAD-I | 29/08/2023 | 05/09/2023 | GREEN VIEW PROJECT INDIA | 2.5 | 1.22 | 48.89 | 100
12 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Retrofitting work at Inayetpur and Ektarpur under Simurali (Zone-IX) W/S Scheme under Surface based Chakdah (Part) Water Supply Scheme under JJM under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000155/2023-2024 | 2114/NAD-I | 01/09/2023 | 16/09/2023 | BIDYUT KUMAR | 30.26 | 14.89 | 49.2 | 100
13 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Interconnection between node 6 to node 382, node 340 to node 355 and providing FHTC (Functional Household Tap Connection) for augmentation work at Suturgachi, Simurali Railgate and Santipally in connection with augmentation of Simurali Zone-X W/S Scheme under Chakdah (Part) W/S Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.17) | Assistant Engineer-II | Junior Engineer-III | ORD/000159/2023-2024 | 2117/NAD-I | 04/09/2023 | 25/09/2023 | BUDDHADEV MONDAL | 74.38 | 73.61 | 98.97 | 100
14 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Interconnection between Inlet and outlet pipe and OHR and bypass arrangement at Joykrishnapur ( Zone- II ) under Chakdah surface water supply scheme inconnection with augmentation of Joykrishnapur W/S Scheme under JJM under Nadia Arsenic Division- I P.H.E Dte(Sl.no.15) | Assistant Engineer-II | Junior Engineer-IV | ORD/000185/2023-2024 | 2156/NAD-I | 08/09/2023 | 29/09/2023 | TARUN KUMAR BHATTACHARYA | 13.76 | 10.34 | 75.13 | 100
15 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Interconnection between Washout/Overflowpipe and delivery pipe at Baeberia H/W site under Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of surface water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000257/2023-2024 | 516/AE-II/NAD-I | 05/12/2023 | 12/12/2023 | BUDDHADEV MONDAL | 2.53 | 1.23 | 48.62 | 100
16 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Retrofitting work of at Manosapota and Malichaghar at Chanduria under Chanduria (Zone-XI) W/S Scheme under Surface based Chakdah (Part) W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000263/2023-2024 | 2725/NAD-I | 06/12/2023 | 27/12/2023 | SUMAN CHAKRABORTY | 18.82 | 8.92 | 47.43 | 100
17 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Zone II (Joykrishnapur) Part - II, Zone-IV(Rukminidanga) Part - III, Zone - VII (Ballavpur) Part - IV, Zone - VIII (Barberia) Part - IV, Zone - X(Shimurali) Part - IV & | SM/11455 | Augmentation | Replacement of pipeline and allied works under Jal Jeevan Mission (JJM) for Chanduria area under Chakdah Block by augmentation of Surface Water Based W/S Scheme for arsenic affected areas of Chakdah (Part Block) of Nadia Dist. Zone-XI (Chanduria) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000280/2023-2024 | 10/AE-II/NAD-I | 04/01/2024 | 11/01/2024 | PRADIP KUMAR BANIK | 2.68 | 1.15 | 43.14 | 100
Total | [13 empty] | 1067.37 | 473.69 | 44.38