## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat - I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Collection of Household Details at prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and submission of same to PHE Dte in soft copy at different piped water supply scheme under Nadia Arsenic Division-I, PHED. Name of PWSS:- 1) Nasra 2) Baganchara 3) Haringhata & Chakdah Zone-VI Part-II 4) Haringhata & Chakdah Zone-VI Part-I 5) Haringhata & Chakdah Zone-VI 6) Gosaichar 7) Saguna 8) Birnagar 9) Parbatipur Zone-I 10) Parbatipur Zone-II 11) Hijuli etc. (Sl. NO. 01) |  |  | ORD/000015/2024-2025 | 977/NAD-I | 25/06/2024 | 23/09/2024 | TECH VISION | 9.88 | 0 | 0 | 0
2 | NADIA | Ranaghat - I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Preparation of Detailed Project Report (DPR) for Gosair Char Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000166/2022-2023 | 3286 /NAD-I | 08/12/2022 | 15/12/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 2.92 | 2.87 | 98.26 | 100
3 | NADIA | Ranaghat - I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Providing, Laying of Rising Main, Laying distribution system and FHTC (Functional Household Tap Connection) under Jal Jivam Mission, Soil investigation for the work of construction of 100 cum OHR staging height 20 mtr, Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including Raft foundation), pipe connection and cost of pipes, specials, Construction of Pump house, Boundary Wall, Service and Allied Works at head work & 2nd site for Gosair Char Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I , PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000217/2023-2024 | 2370/NAD-I | 06/10/2023 | 05/10/2024 | SANJOY BAKSHI | 294.57 | 0 | 0 | 0
4 | NADIA | Ranaghat - I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 845/NAD-I | 04/06/2024 |  | Resource Division | 1.87 | 0 | 0 | 0
5 | NADIA | Ranaghat - I | Nadia Arsenic Division I | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/13758 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 59/NAD-I | 16/01/2024 |  | Resource Division | 3.09 | 0 | 0 | 0
Total | [13 empty] | 312.34 | 2.87 | 0.92