## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhayna Zone- II Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15543 | Augmentation | Augmentation of AIRP capacity (19cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Bhayna Zone-II under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (SL.02) | Assistant Engineer-I | Junior Engineer-IV | ORD/000121/2023-2024 | 1796/NAD-I | 31/07/2023 | 30/08/2023 | M/S R.K. ENTERPRISE | 46.11 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhayna Zone- II Water Supply Scheme, Part-IV under Jal Jeevan Mission(JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I. P.H.E.Dte. | SM/15543 | Augmentation | Load enhancement of Bhayna Z-1 (Ph-1) water supply scheme at Hanskhali block, Dist.-Nadia |  |  | BILL/00333/2024-2025 | BP-22-24-25 | 21/05/2024 |  | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 1.28 | 0 | 0 | null
Total | [13 empty] | 47.4 | 0 | 0