## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | SHIFTING OF POLE AT GANGNAPUR PHE |  |  | BILL/00124/2024-2025 | 100/PFMS | 11/07/2024 | 11/07/2024 | W.B.S.E.D.C.L (GANGNAPURC.C.C) | 0.41 | 0 | 0 | 0
2 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-32 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. |  |  | BILL/00131/2023-2024 | 147/PFMS | 04/07/2023 | 04/07/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.91 | 0 | 0 | 0
3 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-31 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. |  |  | BILL/00132/2023-2024 | 146/PFMS | 04/07/2023 | 04/07/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 6.15 | 0 | 0 | 0
4 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-49 in IR-RBCS is pending for payment. |  |  | BILL/00191/2023-2024 | 179/PFMS | 04/08/2023 | 04/08/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.15 | 0 | 0 | 0
5 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-50 in IR-RBCS is pending for payment. |  |  | BILL/00192/2023-2024 | 178/PFMS | 04/08/2023 | 04/08/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.22 | 0 | 0 | 0
6 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-51 in IR-RBCS is pending for payment. |  |  | BILL/00193/2023-2024 | 180/PFMS | 04/08/2023 | 04/08/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.3 | 0 | 0 | 0
7 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-52 in IR-RBCS is pending for payment. |  |  | BILL/00194/2023-2024 | 177/PFMS | 04/08/2023 | 04/08/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
8 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Bill for Taherpur flag to Badkulla station railway crossing for JJM works under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00273/2023-2024 | 220/PFMS | 20/09/2023 | 20/09/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.25 | 0 | 0 | 0
9 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-49 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00278/2023-2024 | 221/PFMS | 20/09/2023 | 20/09/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 9.96 | 0 | 0 | 0
10 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-50 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00279/2023-2024 | 240/PFMS | 20/09/2023 | 20/09/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 14.94 | 0 | 0 | 0
11 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-51 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00381/2023-2024 | 340/PFMS | 13/11/2023 | 13/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 19.06 | 0 | 0 | 0
12 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00438/2023-2024 | 345/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
13 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00439/2023-2024 | 346/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
14 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00440/2023-2024 | 347/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
15 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00441/2023-2024 | 348/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0 | 0
16 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00442/2023-2024 | 349/PFMS | 23/11/2023 | 23/11/2023 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.32 | 0 | 0 | 0
17 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Shifting of Electric Pole from the proposed GLR Site inside the Campus of water Management Research Station, Begopara (Patuli) Ranaghat-II Block, under Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00506/2023-2024 | 396/PFMS | 18/12/2023 | 18/12/2023 | WBSEDCL | 0.06 | 0 | 0 | 0
18 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Restoration of Road from NH-34 Begopara Church to Nokari Petrol Pump via coopers Camp.(0.938 KM to 3.800 KM |  |  | BILL/00553/2024-2025 | 531/PFMS | 28/03/2025 | 28/03/2025 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 24.79 | 0 | 0 | 0
19 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00561/2023-2024 | 437/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.35 | 0 | 0 | 0
20 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00562/2023-2024 | 438/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0 | 0
21 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00563/2023-2024 | 439/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0 | 0
22 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00564/2023-2024 | 441/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 4.93 | 0 | 0 | 0
23 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00565/2023-2024 | 442/PFMS | 12/01/2024 | 12/01/2024 | FA & CAO, EASTERN RAILWAY, KOLKATA | 20.56 | 0 | 0 | 0
24 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | TARAPUR BALAGARHGHAT ROAD WITH LINK ROAD TO RAVANBERIA GHAT ROAD AT LINK ROAD PORTION FROM 0.00 KMP TO 0.80 KMP (LHS) AND FROM 0.00 KMP TO 1.100 KMP (RHS) -RESTORATION WORK ARSING OUT OFDAMAGE OF BLACKTOP AND HARD SHOULDER FOR LAYING OF uPVC AND D.I PIPELINE FOR"INTEGRATED SURFACE WATER BASED PWSS FOR RANAGHAT-I AND RANAGHAT-II BLOCK UNDER NADIA ARSENIC DIVISION-I,PHE DTE" UNDER NADIA HIGHWAY DIVISION-II IN THE DISTRICT OF NADIA. 50% OF THE AMOUNT(IST INSTALLMENT) IS RECOMMENDED FOR PAYMENT NOW(VIDE PWD CIRCULAR NO-IM-3/16/90/R/PL DATED-22.03.2023 FILE NO-DPHE-84012/28/2024-EENARSBI SEC-DPHE(COMPUTER NO-1081732) |  |  | BILL/00584/2024-2025 | 500/PFMS | 28/03/2025 | 28/03/2025 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 17.83 | 0 | 0 | 0
25 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Hanskhali Bagula Duttapulia Road from 34.35 km to 35.00 km- " Restoration work arising out of damage of blacktop for laying of pipeline for integrated surface water based pwss for Ranaghat-I & Ranaghat-II block under Nadia Arsenic Division-I, P.H.E.Dte" under Nadia Highway Division-II in the district of Nadia *50 % of the amount is recommended (1st installment) for paymeny now ( vide PWD circular no-IM-3/16/90-R/PL Dated - 22.03.2023) * File no- DPHE-84012/28/2024-EENARSDI SEC-DPHE (computer No-1081732) |  |  | BILL/00585/2024-2025 | 499/PFMS | 28/03/2025 | 28/03/2025 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 12.69 | 0 | 0 | 0
26 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | NH-34 to Ravanberia via pyradanga Railway station from 2.195 Kmp to 3.410 Km with crossing -" Restoration work arising out of damage of black top for laying of 200 mm dia DI pipeline under Nadia Arsenic Division-I , P.H.E.Dte" under Nadia Highway Division-II in the district of Nadia *50 % of the amount is recommended (1st installment) for paymeny now ( vide PWD circular no-IM-3/16/90-R/PL Dated - 22.03.2023) * File no- DPHE-84012/28/2024-EENARSDI SEC-DPHE (computer No-1081732) |  |  | BILL/00586/2024-2025 | 501/PFMS | 28/03/2025 | 28/03/2025 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 10.1 | 0 | 0 | 0
27 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Supply of documents for way leave permission from the Eastern Railways authority at 2 nos of locations on Ranaghat-Krishnagar, Ranaghat -Shantipur&Ranaghat-Bongaon Railway track under Intregrated surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. Intersection Name: 1) AV24- AV28 Birnagar Rail Gate) 2) AV61- AV64 Taherpur Rail Gate) | Assistant Engineer-I | Junior Engineer-I | ORD/000114/2023-2024 | 309/AE-I/NAD-I | 28/07/2023 | 26/10/2023 | SUMAN CHAKRABORTY | 3.84 | 0 | 0 | 100
28 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Preparation of Detailed Project Report (DPR) for Integrated Surface Water Based PWSS for Ranaghat-I & Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer-I | Junior Engineer-IV | ORD/000116/2023-2024 | 1610/NAD-I | 22/06/2023 | 07/07/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 57.65 | 0 | 0 | 100
29 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Laying of DI Rising Main of Ranaghat I & II Block, Construction of 4 Nos. 100 Cum GLR, 1 No 50 Cum GLR, Construction of 900, 500, 150& 2 Nos. 1500 M3 OHR at Different Location, 6 Nos. Chlorine Room & 5 Nos. Pump House of Integrated Surface Water Based PWSS for Ranaghat-I and Ranaghat-II Block under Nadia Arsenis Division-I P.H.E. Dte (Sl.no.01) | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II,Junior Engineer-IV | ORD/000135/2023-2024 | 1897/NAD-I | 14/08/2023 | 13/08/2026 | AMAL DUTTA ROY | 3770.77 | 0 | 0 | 90
30 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Laying and repairing of damaged UPVC pipeline of different existing piped water supply schemes under PHED at Ranaghat-I & II Block due to laying of DI Secondary Rising main under Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block, including restoration of village roads by Jhama Metal, Rail/National Way Crossing of pipeline, Pipe Carriage and allied works Under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000174/2024-2025 | 1748/NAD-I | 24/10/2024 | 21/07/2025 | AMAL DUTTA ROY | 474.38 | 0 | 0 | 80
31 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Name of Work: Supply of documents for way leave permission from the Eastern Railways authority at 9 nos of locations on Ranaghat- Krishnagar, Ranaghat- Shantipur & Ranaghat-Bongaon Railway track under Intregrated Surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II,Junior Engineer-IV | ORD/000236/2023-2024 | 2343/NAD-I | 03/10/2023 | 28/10/2023 | SATYABRATA CHAKRABORTY | 17.28 | 0 | 0 | 100
32 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Pond side earth protection with Eucalyptus bullah piling at Kamgachi GLR Site within Ranaght-II Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000303/2023-2024 | 96/AE-I/NAD-I | 27/02/2024 | 13/03/2024 | R R ENTERPRISE | 4.38 | 0 | 0 | 100
33 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1085/NAD-I | 25/04/2023 | 25/04/2023 | Resource Division | 1599.91 | 0 | 0 | 0
34 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1874/NAD-I | 10/08/2023 | 10/08/2023 | Resource Division | 1012.08 | 0 | 0 | 0
35 | NADIA | Ranaghat - I,Ranaghat - II | Nadia Arsenic Division I | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1887/NAD-I | 11/08/2023 | 11/08/2023 | Resource Division | 1117.16 | 0 | 0 | 0
36 | NADIA | Ranaghat - I,Ranaghat - II | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Earnest money for new service connection at Ranaghat GLR-1 of integrated surface water based PWSS. |  |  | BILL/01919/2023-2024 | BP-126-23-24 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.05 | 0 | 0 | 0
37 | NADIA | Ranaghat - I,Ranaghat - II | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | New Service Connection and security deposit for new bulk power supply at Kamgachi Zone-I W/S Scheme. |  |  | BILL/04121/2023-2024 | BP-258-23-24 | 29/12/2023 | 29/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 43.18 | 0 | 0 | 0
38 | NADIA | Ranaghat - I,Ranaghat - II | Eastern Mechanical | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte. | SM/18257 | New | Providing Electro-Mechanical Equipment for 11/0.433 KV Sub-station along with pumping station and disinfection arrangement for GLR-I at Kamgachi under Surface based Water Supply Scheme for Ranaghat-I Block in the District of Nadia. | Assistant Engineer | Junior Engineer | ORD/001685/2023-2024 | 6260/EMD | 10/10/2023 | 30/06/2025 | WEST BENGAL ENGINEERING CO. | 733.62 | 0 | 0 | 53
Total | [13 empty] | 9004.17 | 0 | 0