## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Chapra | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | New Service Connection under AE-III Bhatgachi |  |  | BILL/01861/2023-2024 | BP-101-23-24 | 31/07/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.39 | 0 | 0 | 0
2 | NADIA | Chapra | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | New Service connection for BHATGACHHI w/s scheme p.h No:-1 | Assistant Engineer | Junior Engineer | ORD/000009/2022-2023 | 2867/EMD | 21/07/2022 | 20/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.2 | 0 | 0 | 0
3 | NADIA | Chapra | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | NEW SERVICE CONNECTION CHARGES FOR BHATGACHHI W/S SCHEME P.H. NO P.H. NO 1 | Assistant Engineer | Junior Engineer | ORD/000012/2022-2023 | 2870/EMD | 21/07/2022 | 20/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.04 | 0 | 0 | 0
4 | NADIA | Chapra | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Bhatgachhi W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer | ORD/000096/2022-2023 | 5010/EMD | 03/11/2022 | 03/12/2022 | R.N.S. TRADING | 10.2 | 4.48 | 43.92 | 80
5 | NADIA | Chapra | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied electro-mechanical works,Voltage Stabilizar and Automatic Chlorinator ( in connection with Aug.work related to FHTC) at Pump Hose No.I(Headworks) under Bhatgachhi W/S Scheme District of Nadia NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/000108/2022-2023 | 5093/EMD | 04/11/2022 | 04/12/2022 | KUNDU ELECTRICAL ENTERPRISE | 10.11 | 9.6 | 94.97 | 90
6 | NADIA | Chapra | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Supply delivery of PCC Pole M.s materials and Electrical accessories and installation DTR of HTOH line to WBSEDCL for new service connection at PH-I under Bhatgachi W/S Scheme |  |  | ORD/002687/2022-2023 | 1231/EMSD-III | 21/10/2022 | 20/11/2022 | KUNDU ELECTRICAL ENTERPRISE | 4.19 | 4.19 | 100 | 10
7 | NADIA | Chapra | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | New Service connection bill for BHATGACHHI PIPED WATER SUPPLY SCHEME |  |  | VCH/001928/2022-2023 | BP-2022-23-26 | 02/08/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.04 | 0 | 0 | 0
8 | NADIA | Chapra | Eastern Mechanical | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | New Service connection bill for BHATGACHHI PIPED WATER SUPPLY SCHEME |  |  | VCH/001929/2022-2023 | BP-2022-23-27 | 02/08/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.16 | 0 | 0 | 0
9 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Bhatgachhi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000001/2022-2023 | 209/NACD-II | 05/04/2022 | 04/06/2022 | PRADIP KUMAR BANIK | 5.38 | 5.32 | 98.92 | 100
10 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bhatgachhi and Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000021/2022-2023 | 246/NACD-II | 19/04/2022 | 18/06/2022 | JOY HIND TUBEWELLS | 41.88 | 39.98 | 95.46 | 100
11 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Bhatgachhi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000031/2022-2023 | 18/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | PRADIP KUMAR BANIK | 2.83 | 2.81 | 99.34 | 100
12 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Laying of Rising Main of Bhatgachhi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000036/2022-2023 | 23/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | SOURAV & CO. | 4.53 | 0.93 | 20.55 | 90
13 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Construction for priliminary work of the approch road at Head Works site of Bhatgachhi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000040/2023-2024 | 405/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | SUDHAMAY MAJUMDAR | 0.96 | 0 | 0 | 0
14 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Bhatgachhi and adjoining mouzas under Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000074/2022-2023 | 299/NACD-II | 19/05/2022 | 17/08/2022 | SATYABRATA CHAKRABORTY | 236.84 | 135.9 | 57.38 | 100
15 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bhatgachhi) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000081/2023-2024 | 887/NACD-II | 18/08/2023 | 08/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
16 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Earthwork in filling in approach road at Bhatgachhi Water Supply Scheme at Bhatgachhi H/W site under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000121/2022-2023 | 112/AE-I/NACD-II | 28/06/2022 | 28/07/2022 | M/S RAJESH CONSTRUCTION | 4.83 | 4.81 | 99.69 | 100
17 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations new vested land under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bhatgachhi) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000149/2024-2025 | 1068/NACD-II | 12/08/2024 | 02/09/2024 | JADAVPUR UNIVERSITY | 4.78 | 2.39 | 50 | 100
18 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Additional Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Bhatgachhi and adjoining mouzas under Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000181/2022-2023 | 523/NACD-II | 05/08/2022 | 04/10/2022 | INVENT ENGINEER'S COOP SOCIETY LTD. | 71.56 | 66.55 | 93 | 100
19 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Bhatgachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000189/2022-2023 | 619/NACD-II | 06/09/2022 | 26/09/2022 | RAMASISH ENTERPRISE | 4.39 | 4.39 | 100 | 100
20 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 43 cum/Hour capacity for Bhatgachhi Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000191/2024-2025 | 1151/NACD-II | 27/08/2024 | 23/02/2025 | SINGHA ROY & CO. | 173.86 | 0 | 0 | 0
21 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Bhatgachhi W/s Scheme, Dhopahat W/s Scheme, Hatkhola W/s Scheme | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000297/2021-2022 | 249/AE-I/NACD-II | 25/02/2022 | 12/03/2022 | PROSENJIT DAS | 2.44 | 2.44 | 100 | 100
22 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Bhatgachhi Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000313/2022-2023 | 77/NACD-II | 10/01/2023 | 11/03/2023 | M/S FREEDOM CONSTRUCTION | 14.78 | 10.57 | 71.5 | 85
23 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Acceptance cum work order "Construction of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir at Head Works site of Tengra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000325/2023-2024 | 337/NACD-II | 05/03/2024 | 05/03/2025 | CHATTERJEE CONSTRUCTION | 94.23 | 0 | 0 | 0
24 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Bhatgachhi 2nd Tubwell site within Bhatgachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000327/2022-2023 | 116/NACD-II | 11/01/2023 | 12/03/2023 | M/S SANTOSHI MAA ENTERPRISE | 5.12 | 4.84 | 94.54 | 85
25 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Renovation of Arsenic cum Iron treatment Plant of Bahirgachhi Zone-II PWSS (Capacity- 23 m3/hr) and Bhatgachhi PWSS ancillary works of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000361/2023-2024 | 35/NACD-II | 09/01/2024 | 09/03/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.51 | 8.38 | 8.33 | 80
26 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Bhatgachhi water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000373/2022-2023 | 355/NACD-II | 22/03/2023 | 16/03/2024 | SUDHAMAY MAJUMDAR | 116.75 | 0 | 0 | 5
27 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 399/NACD-II | 04/07/2022 |  | Resource Division | 51.43 | 0 | 0 | 0
28 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000238/2022-2023 | null | 20/09/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
29 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000239/2022-2023 | null | 20/09/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
30 | NADIA | Chapra | Nadia Arsenic Civil Division II | BHATGACHHI PIPED WATER SUPPLY SCHEME | SM/10099 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000345/2022-2023 | 141 | 01/11/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
Total | [13 empty] | 973.25 | 312.34 | 32.09