## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta - I | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | New connection charges for Kanainagra PHE I |  |  | BILL/00222/2022-2023 | 106/PFMS/EMD | 16/12/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0 | 0
2 | NADIA | Tehatta - I | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | New connection charges for Kanainagra PHE II |  |  | BILL/00224/2022-2023 | 107/PFMS/EMD | 16/12/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0 | 0
3 | NADIA | Tehatta - I | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Electriciyy bill pay for the new service connection at Kanaigar PHE II |  |  | BILL/02157/2022-2023 | 153/PFMS/EMD | 13/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.76 | 0 | 0 | 0
4 | NADIA | Tehatta - I | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Electriciyy bill pay for the new service connection at Kanaigar PHE I |  |  | BILL/02158/2022-2023 | 154/PFMS/EMD | 13/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.63 | 0 | 0 | 0
5 | NADIA | Tehatta - I | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Kanainagar W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000452/2022-2023 | 6262/EMD | 19/11/2022 | 19/12/2022 | TARUN KUMAR BHATTACHARYA | 10.05 | 4.95 | 49.19 | 100
6 | NADIA | Tehatta - I | Eastern Mechanical | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Kanainagar W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 6370/EMD | 23/11/2022 | 23/12/2022 | S.R. CONCERN | 10.05 | 9.53 | 94.79 | 100
7 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Kanainagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000009/2022-2023 | 207/NACD-II | 05/04/2022 | 04/06/2022 | A.K ADHIKARY | 5.37 | 5.35 | 99.51 | 100
8 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Kanainagar and Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000019/2022-2023 | 244/NACD-II | 19/04/2022 | 18/06/2022 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 38.44 | 90.66 | 100
9 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Kanainagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000045/2022-2023 | 12/AE-II/NACD-II | 11/04/2022 | 10/06/2022 | A.K ADHIKARY | 2.83 | 2.81 | 99.53 | 100
10 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Construction of approch road at Head Works site of Kanainagar Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000049/2023-2024 | 415/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0.48 | 49.98 | 100
11 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Laying of Rising Main of Kanainagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000059/2022-2023 | 20/AE-II/NACD-II | 18/04/2022 | 18/05/2022 | CHINMOY BISWAS | 4.98 | 2.48 | 49.83 | 100
12 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Kanainagar and adjoining mouzas under Kanainagar Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000072/2022-2023 | 340/NACD-II | 03/06/2022 | 01/09/2022 | B.M. ENGINEERING & CONSTRUCTION | 285.26 | 235.34 | 82.5 | 100
13 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Kanainagar and Dhopahat PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000182/2024-2025 | 296_AE-II/NACD-II | 30/08/2024 | 19/09/2024 | MAKALI ENGINEERING CORPORATION | 4.81 | 2.4 | 50 | 0
14 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Kanainagar Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000198/2022-2023 | 627/NACD-II | 06/09/2022 | 26/09/2022 | MAKALI ENGINEERING CORPORATION | 4.94 | 4.94 | 100 | 100
15 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Kanainagar Water Supply Scheme Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000321/2022-2023 | 85/NACD-II | 10/01/2023 | 11/03/2023 | SUMIT GHOSH | 14.7 | 11.76 | 80.01 | 85
16 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Kanainagar 2nd Tubewell Site within Kanainagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000331/2022-2023 | 124/NACD-II | 11/01/2023 | 12/03/2023 | CHINMOY BISWAS | 5.66 | 5.36 | 94.71 | 85
17 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Construction of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Kanainagar water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000377/2022-2023 | 370/NACD-II | 23/03/2023 | 17/03/2024 | B.M. ENGINEERING & CONSTRUCTION | 143.29 | 54.27 | 37.88 | 35
18 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 409/NACD-II | 04/07/2022 |  | Resource Division | 51.88 | 0 | 0 | 0
19 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000240/2022-2023 | null | 20/09/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
20 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | KANAINAGAR PIPED WATER SUPPLY SCHEME | SM/10406 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000346/2022-2023 | 141 | 01/11/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
Total | [13 empty] | 595.14 | 378.13 | 63.54