## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta - I | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | New connection charges for Mrigi PHE II |  |  | BILL/00226/2022-2023 | 109/PFMS/EMD | 16/12/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0 | 0
2 | NADIA | Tehatta - I | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | New connection charges for Mrigi PHE I |  |  | BILL/00228/2022-2023 | 108/PFMS/EMD | 16/12/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.37 | 0 | 0 | 0
3 | NADIA | Tehatta - I | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Electriciyy bill pay for the new service connection at Migri PHE II |  |  | BILL/02155/2022-2023 | null | 03/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.22 | 0 | 0 | 0
4 | NADIA | Tehatta - I | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Electriciyy bill pay for the new service connection at Migri PHE I |  |  | BILL/02156/2022-2023 | null | 03/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.41 | 0 | 0 | 0
5 | NADIA | Tehatta - I | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Electricity bill pay for the new service connection at Mrigi PHE II |  |  | BILL/02322/2022-2023 | 151/PFMS/EMD | 13/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.22 | 0 | 0 | 0
6 | NADIA | Tehatta - I | Eastern Mechanical | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Electricity bill pay for the new service connection at Mrigi PHE I |  |  | BILL/02323/2022-2023 | 152/PFMS/EMD | 13/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.41 | 0 | 0 | 0
7 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Mrigi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000010/2022-2023 | 208/NACD-II | 05/04/2022 | 04/06/2022 | ROY CONSTRUCTION | 5.37 | 5.37 | 99.99 | 100
8 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Kanainagar and Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000019/2022-2023 | 244/NACD-II | 19/04/2022 | 18/06/2022 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 0 | 0 | 100
9 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Mrigi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000046/2022-2023 | 13/AE-II/NACD-II | 11/04/2022 | 10/06/2022 | ROY CONSTRUCTION | 2.83 | 2.83 | 100 | 100
10 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Mrigi and adjoining mouzas under Mrigi Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000056/2022-2023 | 284/NACD-II | 11/05/2022 | 09/08/2022 | CHANDA CONSTRUCTION | 217.71 | 162.98 | 74.86 | 90
11 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte.(Phase-I) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000056/2024-2025 | 165_AE-II/NACD-II | 14/06/2024 | 14/07/2024 | M/S RAJESH CONSTRUCTION | 0.97 | 0.48 | 49.85 | 100
12 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Earthwork for protection of the existing structures and hydraulic arrangement in the ongoing Mrigi Public Water Supply Scheme (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000057/2024-2025 | 166/AE-II/NACD-II | 14/06/2024 | 29/06/2024 | R.M.TRADING | 0.95 | 0.48 | 49.94 | 100
13 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Laying of Rising Main of Mrigi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000061/2022-2023 | 22/AE-II/NACD-II | 18/04/2022 | 18/05/2022 | R.M. TRADING | 3.73 | 0.84 | 22.45 | 85
14 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Mrigi) |  | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000114/2023-2024 | 1153/NACD-II | 10/10/2023 | 31/10/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
15 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Earth work in filling in ditches at Mrigi 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000124/2022-2023 | 60/AE-II/NACD-II | 28/06/2022 | 13/07/2022 | SURAJIT KUMAR GHOSH | 2.26 | 2.26 | 99.92 | 100
16 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte.(Phase-II) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000146/2024-2025 | 248/AE-II/NACD-II | 31/07/2024 | 15/08/2024 | R.M.TRADING | 0.95 | 0.47 | 49.97 | 100
17 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Construction of approch road at Head Works site of Mrigi Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000151/2023-2024 | 516/AE-I/NACD-II | 18/12/2023 | 02/01/2024 | CHANDA CONSTRUCTION | 0.97 | 0 | 0 | 0
18 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Smoothening of site by land filling of existing undulation by filling the ditches at Mrigi 2nd Tube Well Site for development of land and compaction by hand roller in connection with T/W Sinking at Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000153/2023-2024 | 518/AE-I/NACD-II | 18/12/2023 | 02/01/2024 | R.M. TRADING | 0.96 | 0.48 | 49.72 | 100
19 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Earthwork for protection of the existing structures and hydraulic arrangement in the ongoing Mrigi Public Water Supply Scheme (Phase-III) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000177/2024-2025 | 291AE-II/NACD-II | 30/08/2024 | 14/09/2024 | M/S RAJESH CONSTRUCTION | 0.96 | 0.48 | 49.63 | 0
20 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Mrigi Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000199/2022-2023 | 628/NACD-II | 06/09/2022 | 26/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.14 | 4.14 | 100 | 100
21 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Mrigi Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000200/2024-2025 | 1069/NACD-II | 12/08/2024 | 08/02/2025 | MANGES INDUSTRIAL CORPORATION. | 164.31 | 0 | 0 | 0
22 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Geotechnical protection work to counterbalance the uneven earth pressure in consultation with relevant I.S. Codes in Mrigi Water Supply Scheme in Tehatta -I Block in Nadia District under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000227/2023-2024 | 164/NACD-II | 07/02/2024 | 22/02/2024 | TARUN GHOSH | 12.36 | 4.92 | 39.84 | 100
23 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Providing 1 no. Guard at Mrigi 2nd Tubewell Water Supply Scheme for guarding of various Departmental materials under Nadia Arsenic Civil Division-II,P.H.E. Dte..[Period of work :01/02/2024 to 31/05/2024] |  |  | ORD/000232/2023-2024 | 602/AE-I/NACD-II | 31/01/2024 | 30/05/2024 | SANDIP ROY | 0.96 | 0 | 0 | 0
24 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Mrigi W/s Scheme, Panchdara Abhaynagar W/s Scheme, Paninala W/s Scheme | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000300/2021-2022 | 252/AE-I/NACD-II | 25/02/2022 | 12/03/2022 | PROSENJIT DAS | 2.44 | 2.44 | 100 | 100
25 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Mrigi Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000323/2022-2023 | 87/NACD-II | 10/01/2023 | 11/03/2023 | PRADUT GHOSH | 16.44 | 4.92 | 29.93 | 85
26 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Mrigi 2nd Tubewell Site within Mrigi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000333/2022-2023 | 126/NACD-II | 11/01/2023 | 12/03/2023 | GHOSH ENTERPRISE | 9 | 3.97 | 44.1 | 85
27 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Mrigi water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000386/2022-2023 | 393/NACD-II | 28/03/2023 | 22/03/2024 | CHANDA CONSTRUCTION | 113 | 36.63 | 32.42 | 20
28 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 402/NACD-II | 04/07/2022 |  | Resource Division | 26.26 | 0 | 0 | 0
29 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000241/2022-2023 | null | 20/09/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
30 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | MRIGI PIPED WATER SUPPLY SCHEME | SM/10408 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000347/2022-2023 | 141 | 01/11/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
Total | [13 empty] | 648.72 | 238.47 | 36.76