## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta - I | Eastern Mechanical | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | New Service Connection at Pump House-I under Binodnagar Water Supply Scheme |  |  | BILL/01877/2023-2024 | BP-109-23-24 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0 | 0
2 | NADIA | Tehatta - I | Eastern Mechanical | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Quotation for new Service connection at P.H-II under Binodnagar W/S Scheme, Dist-Nadia |  |  | BILL/04634/2023-2024 | BP-283-23-24 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 4.61 | 0 | 0 | 0
3 | NADIA | Tehatta - I | Eastern Mechanical | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under BINODNAGAR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000030/2023-2024 | 1609/EMD | 26/04/2023 | 26/05/2023 | ABHISEK ENGINEERING CONCERN | 18.99 | 0 | 0 | 80
4 | NADIA | Tehatta - I | Eastern Mechanical | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at BINODNAGAR Piped Water SupplyScheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. |  | Junior Engineer | ORD/001121/2023-2024 | 4709/EMD | 04/08/2023 | 03/09/2023 | M/S DILIP MITRA | 40.82 | 0 | 0 | 0
5 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00019/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
6 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00092/2022-2023 | 235/7 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
7 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Construction of approch road at Head Works site of Binodnagar Water Supply Scheme in Tehatta-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000043/2023-2024 | 408/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0 | 0 | 100
8 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Binodnagar) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000082/2023-2024 | 888/NACD-II | 18/08/2023 | 08/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 100
9 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Binodnagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000111/2023-2024 | 1170/NACD-II | 11/10/2023 | 25/11/2023 | R.M. TRADING | 11.32 | 0 | 0 | 90
10 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Binodnagar water supply scheme under Tehatta- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000135/2023-2024 | 1253/NACD-II | 08/11/2023 | 23/12/2023 | SURAJIT KUMAR GHOSH | 34.92 | 0 | 0 | 100
11 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Binodnagar and Putimari PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000180/2024-2025 | 294_AE-II/NACD-II | 30/08/2024 | 19/09/2024 | MAKALI ENGINEERING CORPORATION | 4.17 | 0 | 0 | 100
12 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Binodnagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000278/2022-2023 | 1133/NACD-II | 16/12/2022 | 15/01/2023 | GENUINE | 21.45 | 0 | 0 | 100
13 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Acceptance cum work order "Conversion of IEP to AIRP at Mobarakpur, Binodnagar & Taranipur Water Supply Scheme of capacity 93 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000282/2023-2024 | 152/NACD-II | 02/02/2024 | 02/04/2024 | B.M. ENGINEERING & CONSTRUCTION | 241.81 | 0 | 0 | 0
14 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 46.51 cum/Hour capacity for Binodnagar Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000296/2024-2025 | 1475/NACD-II | 12/11/2024 | 11/05/2025 | B.M. ENGINEERING & CONSTRUCTION | 177.87 | 0 | 0 | 0
15 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Binodnagar Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000390/2022-2023 | 397/NACD-II | 28/03/2023 | 28/03/2025 | B.M. ENGINEERING & CONSTRUCTION | 298.5 | 0 | 0 | 52
16 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Smoothening of site by land filling of existing undulation by filling the ditches at Binodnagar 2nd Tube Well Site for development of land and compaction by hand roller for approch road at Binodnagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000402/2024-2025 | 409/AE-II/NACD-II | 31/01/2025 | 17/03/2025 | M/S. SANTOSHI MAA ENTERPRISE | 0.95 | 0 | 0 | 100
17 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Installation of Sign Board for Demarcation of Land for Binodnagar & other PWSS at Tehatta-I, Barnia & other PWSS at Tehatta-II, Karimpur-II, Jayrampur & other PWSS at Karimpur-I & Maniknagar PWSS at Shantipur Block under Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000430/2024-2025 | 1193/AE-I/NACD-II | 25/02/2025 | 11/04/2025 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 3.79 | 0 | 0 | 60
18 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 1089/NACD-II | 09/12/2022 | 09/12/2022 | Resource Division | 33.57 | 0 | 0 | 0
19 | NADIA | Tehatta - I | Nadia Arsenic Civil Division II | BINODNAGAR PIPED WATER SUPPLY SCHEME | SM/11965 | New | Material Requisition To Resource Division |  |  | RTOR000029/2022-2023 | 374/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 11.09 | 0 | 0 | 0
Total | [13 empty] | 913.21 | 0 | 0