## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) | SM/08777 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gaighata Water Supply Scheme at Gaighata Block within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000642/2021-2022 | 2174/BD | 18/11/2021 | 16/02/2022 | SINGHA ROY & CO. | 133.93 | 129.03 | 96.34 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) | SM/08777 | Retrofitting | Acceptance cum work order for Estimate for Additional Survey Work For DPR Preparation of Bhabanipur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000978/2021-2022 | 2157/HSD | 28/12/2021 | 18/01/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.47 | 3.44 | 99.09 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) | SM/08777 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Bagdah Water Supply Scheme under Bongaon Sub-Division, under Barasat Division,PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001114/2021-2022 | 608/Bon | 31/12/2021 | 20/01/2022 | UMWELT ENGINEER PVT.LTD. | 4.27 | 4.27 | 100 | 1
4 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) | SM/08777 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Sindrani (Zone-I) Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002033/2021-2022 | 609/Bon | 31/12/2021 | 20/01/2022 | UMWELT ENGINEER PVT.LTD. | 4.14 | 4.14 | 100 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gaighata Piped Water Supply Scheme at Gaighata Block (Phase-I) | SM/08777 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 252/BD | 27/01/2022 |  | Resource Division | 1.99 | 0 | 0 | 0
Total | [13 empty] | 147.81 | 140.88 | 95.32