## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Minakhan GP from 27.05.21 to 03.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000388/2021-2022 | 405/HSD(Camp) | 27/05/2021 | 04/06/2021 | MONDAL & CO. (BASIRHAT). | 4.58 | 4.58 | 100 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bamanpukur GP from 27.05.21 to 03.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000389/2021-2022 | 406/HSD(Camp) | 27/05/2021 | 04/06/2021 | MONDAL & CO. (BASIRHAT). | 4.8 | 4.8 | 100 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 27.05.21 to 30.05.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000390/2021-2022 | 407/HSD(Camp) | 27/05/2021 | 31/05/2021 | TRISHA ENTERPRISE & CO. | 4.77 | 4.77 | 100 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 31.05.21 to 06.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000391/2021-2022 | 408/HSD(Camp) | 27/05/2021 | 03/06/2021 | MONDAL & CO. (BASIRHAT). | 4.51 | 4.51 | 100 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 27.05.21 to 30.05.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000392/2021-2022 | 409/HSD(Camp) | 27/05/2021 | 31/05/2021 | TRISHA ENTERPRISE & CO. | 4.81 | 4.81 | 100 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 31.05.21 to 06.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000393/2021-2022 | 410/HSD(Camp) | 27/05/2021 | 03/06/2021 | MONDAL & CO. (BASIRHAT). | 4.55 | 4.55 | 100 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 27.05.21 to 28.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000407/2021-2022 | 423/HSD(Camp) | 27/05/2021 | 29/05/2021 | M/S NIRMAN CONSTRUCTION. | 4.94 | 4.94 | 100 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 29.05.21 to 03.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000408/2021-2022 | 424/HSD(Camp) | 27/05/2021 | 02/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.85 | 4.85 | 100 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000413/2021-2022 | 429/HSD(Camp) | 27/05/2021 | 30/05/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.49 | 4.49 | 100 | 0
10 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000414/2021-2022 | 430/HSD(Camp) | 27/05/2021 | 04/06/2021 | S.K.ENTERPRISE. | 4.76 | 4.76 | 100 | 0
11 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP on 27.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000420/2021-2022 | 436/HSD(Camp) | 27/05/2021 | 28/05/2021 | MONDAL & CO. (BASIRHAT). | 4.78 | 4.78 | 100 | 0
12 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 27.05.21 to 30.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000422/2021-2022 | 438/HSD(Camp) | 27/05/2021 | 31/05/2021 | M/S PROGATI ENTERPRISE. | 4.7 | 4.7 | 100 | 0
13 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 28.05.21 to 31.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000430/2021-2022 | 446/HSD(Camp) | 27/05/2021 | 31/05/2021 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 100 | 0
14 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 31.05.21 to 06.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000433/2021-2022 | 449/HSD(Camp) | 27/05/2021 | 03/06/2021 | M/S PROGATI ENTERPRISE. | 4.69 | 4.69 | 100 | 0
15 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 31.05.21 to 06.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000434/2021-2022 | 450/HSD(Camp) | 27/05/2021 | 03/06/2021 | M/S DATTA ENTERPRISE. | 4.69 | 4.69 | 100 | 0
16 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 01.06.21 to 04.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000435/2021-2022 | 451/HSD(Camp) | 27/05/2021 | 31/05/2021 | MONDAL & CO. (BASIRHAT). | 4.73 | 4.73 | 100 | 0
17 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 04.06.21 to 09.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000439/2021-2022 | 470/HSD(Camp) | 03/06/2021 | 09/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.85 | 4.85 | 100 | 0
18 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Monipur GP from 10.06.21 to 15.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000440/2021-2022 | 471/HSD(Camp) | 03/06/2021 | 09/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.85 | 4.85 | 100 | 0
19 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000444/2021-2022 | 475/HSD(Camp) | 03/06/2021 | 11/06/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.76 | 4.76 | 100 | 0
20 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Minakhan GP from 04.06.21 to 15.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000458/2021-2022 | 489/HSD(Camp) | 03/06/2021 | 15/06/2021 | MONDAL & CO. (BASIRHAT). | 4.85 | 4.85 | 100 | 0
21 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bamanpukur GP from 04.06.21 to 15.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000459/2021-2022 | 490/HSD(Camp) | 03/06/2021 | 15/06/2021 | MONDAL & CO. (BASIRHAT). | 4.85 | 3.34 | 68.83 | 0
22 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 07.06.21 to 13.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000460/2021-2022 | 491/HSD(Camp) | 03/06/2021 | 10/06/2021 | TRISHA ENTERPRISE & CO. | 4.53 | 4.53 | 100 | 0
23 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 07.06.21 to 13.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000461/2021-2022 | 492/HSD(Camp) | 03/06/2021 | 10/06/2021 | MONDAL & CO. (BASIRHAT). | 4.53 | 4.53 | 100 | 0
24 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 05.06.21.21 to 08.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000465/2021-2022 | 496/HSD(Camp) | 03/06/2021 | 07/06/2021 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 100 | 0
25 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bhabanipur GP from 06.06.21 to 11.06.21 due to cyclone 'YAAS', Hasnabad block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000467/2021-2022 | 498/HSD(Camp) | 03/06/2021 | 09/06/2021 | M/S K.B.ENTERPRISE. | 3.07 | 3.07 | 100 | 0
26 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 07.06.21 to 13.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer |  | ORD/000468/2021-2022 | 499/HSD(Camp) | 03/06/2021 | 10/06/2021 | M/S DATTA ENTERPRISE. | 4.68 | 4.68 | 100 | 0
27 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 07.06.21 to 13.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000469/2021-2022 | 500/HSD(Camp) | 03/06/2021 | 10/06/2021 | M/S DATTA ENTERPRISE. | 4.69 | 4.69 | 100 | 0
28 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 09.06.21.21 to 12.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000470/2021-2022 | 501/HSD(Camp) | 03/06/2021 | 07/06/2021 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 100 | 0
29 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Minakhan GP from 16.06.21 to 27.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000485/2021-2022 | 522/HSD(Camp) | 14/06/2021 | 26/06/2021 | MONDAL & CO. (BASIRHAT). | 4.85 | 4.85 | 100 | 0
30 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bamanpukur GP from 16.06.21 to 27.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000486/2021-2022 | 523/HSD(Camp) | 14/06/2021 | 26/06/2021 | TRISHA ENTERPRISE & CO. | 4.85 | 4.85 | 100 | 0
31 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Bamanpukur GP from 28.06.21 to 03.07.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000487/2021-2022 | 524/HSD(Camp) | 14/06/2021 | 20/06/2021 | MONDAL & CO. (BASIRHAT). | 1.82 | 1.82 | 100 | 0
32 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 14.06.21 to 20.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000488/2021-2022 | 525/HSD(Camp) | 14/06/2021 | 21/06/2021 | TRISHA ENTERPRISE & CO. | 4.53 | 4.53 | 100 | 0
33 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Mohanpur GP from 21.06.21 to 28.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000489/2021-2022 | 526/HSD(Camp) | 14/06/2021 | 22/06/2021 | MONDAL & CO. (BASIRHAT). | 4.86 | 4.86 | 100 | 0
34 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 14.06.21 to 20.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000490/2021-2022 | 527/HSD(Camp) | 14/06/2021 | 21/06/2021 | MONDAL & CO. (BASIRHAT). | 4.53 | 4.53 | 100 | 0
35 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Atpukur GP from 21.06.21 to 28.06.21 due to cyclone 'YAAS', Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000491/2021-2022 | 528/HSD(Camp) | 14/06/2021 | 22/06/2021 | MONDAL & CO. (BASIRHAT). | 4.86 | 4.86 | 100 | 0
36 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Disinfection & repairing of tube wells at different places in different GPs within Minakhan block due to cyclone 'YAAS' under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000492/2021-2022 | 529/HSD(Camp) | 14/06/2021 | 21/06/2021 | TRISHA ENTERPRISE & CO. | 3.71 | 3.71 | 100 | 0
37 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 26.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000509/2021-2022 | 546/HSD(Camp) | 14/06/2021 | 18/06/2021 | M/S NIRMAN CONSTRUCTION. | 2.77 | 2.77 | 100 | 0
38 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Korakati GP from 27.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000512/2021-2022 | 549/HSD(Camp) | 14/06/2021 | 17/06/2021 | M/S NIRMAN CONSTRUCTION. | 1.78 | 1.78 | 100 | 0
39 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 15.06.21 to 20.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000513/2021-2022 | 550/HSD(Camp) | 14/06/2021 | 20/06/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.75 | 4.75 | 100 | 0
40 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 21.06.21 to 26.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000514/2021-2022 | 551/HSD(Camp) | 14/06/2021 | 20/06/2021 | S.K.ENTERPRISE. | 4.76 | 4.76 | 100 | 0
41 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Khulna GP from 27.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000515/2021-2022 | 552/HSD(Camp) | 14/06/2021 | 17/06/2021 | M/S NIRMAN CONSTRUCTION. | 1.78 | 1.78 | 100 | 0
42 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sahebkhali GP from 14.06.21 to 20.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000523/2021-2022 | 560/HSD(Camp) | 14/06/2021 | 21/06/2021 | M/S DATTA ENTERPRISE. | 4.68 | 4.68 | 100 | 0
43 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 14.06.21 to 20.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer |  | ORD/000524/2021-2022 | 561/HSD(Camp) | 14/06/2021 | 21/06/2021 | M/S PROGATI ENTERPRISE. | 4.68 | 4.68 | 100 | 0
44 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Rupamari GP from 21.06.21.21 to 24.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000532/2021-2022 | 569/HSD(Camp) | 14/06/2021 | 18/06/2021 | MONDAL & CO. (BASIRHAT). | 4.73 | 4.73 | 100 | 0
45 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Dulduli GP from 21.06.21 to 27.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000534/2021-2022 | 571/HSD(Camp) | 14/06/2021 | 21/06/2021 | M/S DATTA ENTERPRISE. | 4.68 | 4.68 | 100 | 0
46 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS in HINGALGANJ & HASNABAD block duly affected by cyclonic storm YAAS. | SM/09152 | Disaster | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 2241/BD | 24/11/2021 |  | Resource Division | 10.26 | 0 | 0 | 0
Total | [13 empty] | 209.46 | 197.68 | 94.38