## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000396/2021-2022 | 413/HSD(Camp) | 27/05/2021 | 30/05/2021 | M/S DATTA ENTERPRISE. | 4.71 | 4.71 | 100 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 30.05.21 to 05.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000397/2021-2022 | 414/HSD(Camp) | 27/05/2021 | 03/06/2021 | M/S PROGATI ENTERPRISE. | 4.69 | 4.69 | 100 | 0
3 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000398/2021-2022 | 415/HSD(Camp) | 27/05/2021 | 30/05/2021 | M/S DATTA ENTERPRISE. | 4.49 | 4.49 | 100 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000399/2021-2022 | 416/HSD(Camp) | 27/05/2021 | 04/06/2021 | M/S PROGATI ENTERPRISE. | 4.75 | 4.75 | 100 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000400/2021-2022 | 417/HSD(Camp) | 27/05/2021 | 30/05/2021 | M/S PROGATI ENTERPRISE. | 4.58 | 4.58 | 100 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000401/2021-2022 | 418/HSD(Camp) | 27/05/2021 | 04/06/2021 | M/S DATTA ENTERPRISE. | 4.86 | 4.86 | 100 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hatgachi GP from 27.05.21 to 04.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000404/2021-2022 | 421/HSD(Camp) | 27/05/2021 | 05/06/2021 | M/S DATTA ENTERPRISE. | 4.67 | 4.67 | 100 | 0
8 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 27.05.21 to 29.05.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000415/2021-2022 | 431/HSD(Camp) | 27/05/2021 | 30/05/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.89 | 4.89 | 100 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 30.05.21 to 06.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000416/2021-2022 | 432/HSD(Camp) | 27/05/2021 | 04/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.91 | 4.91 | 100 | 0
10 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP on 27.05.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer |  | ORD/000421/2021-2022 | 437/HSD(Camp) | 27/05/2021 | 28/05/2021 | MONDAL & CO. (BASIRHAT). | 4.43 | 4.43 | 100 | 0
11 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 11, 12, 14 from 27.05.21 to 31.05.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000424/2021-2022 | 440/HSD(Camp) | 27/05/2021 | 01/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.64 | 4.64 | 100 | 0
12 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 28.05.21 to 02.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000431/2021-2022 | 447/HSD(Camp) | 27/05/2021 | 02/06/2021 | TRISHA ENTERPRISE & CO. | 4.9 | 4.9 | 100 | 0
13 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 11, 12, 14 from 01.06.21 to 11.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000437/2021-2022 | 453/HSD(Camp) | 27/05/2021 | 07/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.76 | 4.76 | 100 | 0
14 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Durgamandop GP from 12.06.21 to 18.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000442/2021-2022 | 473/HSD(Camp) | 03/06/2021 | 10/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.86 | 4.86 | 100 | 0
15 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000445/2021-2022 | 476/HSD(Camp) | 03/06/2021 | 11/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.9 | 4.9 | 100 | 0
16 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 06.06.21 to 12.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000451/2021-2022 | 482/HSD(Camp) | 03/06/2021 | 10/06/2021 | M/S PROGATI ENTERPRISE. | 4.68 | 4.68 | 100 | 0
17 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000452/2021-2022 | 483/HSD(Camp) | 03/06/2021 | 11/06/2021 | M/S DATTA ENTERPRISE. | 4.76 | 4.76 | 100 | 0
18 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 07.06.21 to 14.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000453/2021-2022 | 484/HSD(Camp) | 03/06/2021 | 11/06/2021 | M/S PROGATI ENTERPRISE. | 4.85 | 4.85 | 100 | 0
19 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hatgachi GP from 05.06.21 to 18.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000456/2021-2022 | 487/HSD(Camp) | 03/06/2021 | 17/06/2021 | M/S PROGATI ENTERPRISE. | 4.67 | 4.67 | 100 | 0
20 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 03.06.21 to 08.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000462/2021-2022 | 493/HSD(Camp) | 03/06/2021 | 09/06/2021 | MONDAL & CO. (BASIRHAT). | 4.89 | 4.89 | 100 | 0
21 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 09.06.21 to 14.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000471/2021-2022 | 502/HSD(Camp) | 03/06/2021 | 09/06/2021 | MONDAL & CO. (BASIRHAT). | 4.9 | 4.9 | 100 | 0
22 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 11, 12, 14 from 12.06.21 to 22.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000473/2021-2022 | 504/HSD(Camp) | 03/06/2021 | 14/06/2021 | M/S RAJPATH CONSTRUCTION. | 4.76 | 4.76 | 100 | 0
23 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 13.06.21 to 19.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000474/2021-2022 | 505/HSD(Camp) | 03/06/2021 | 10/06/2021 | M/S DATTA ENTERPRISE. | 4.69 | 4.69 | 100 | 0
24 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Kalinagar GP from 20.06.21 to 27.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000495/2021-2022 | 532/HSD(Camp) | 14/06/2021 | 22/06/2021 | M/S PROGATI ENTERPRISE. | 4.9 | 4.9 | 100 | 0
25 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 15.06.21 to 22.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000496/2021-2022 | 533/HSD(Camp) | 14/06/2021 | 22/06/2021 | M/S DATTA ENTERPRISE. | 4.76 | 4.75 | 100 | 0
26 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-I GP from 23.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000497/2021-2022 | 534/HSD(Camp) | 14/06/2021 | 21/06/2021 | M/S DATTA ENTERPRISE. | 4.16 | 3.39 | 81.55 | 0
27 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 15.06.21 to 22.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000498/2021-2022 | 535/HSD(Camp) | 14/06/2021 | 22/06/2021 | M/S PROGATI ENTERPRISE. | 4.85 | 4.85 | 100 | 0
28 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Nazat-II GP from 23.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000499/2021-2022 | 536/HSD(Camp) | 14/06/2021 | 22/06/2021 | M/S PROGATI ENTERPRISE. | 4.24 | 4.24 | 100 | 0
29 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hatgachi GP from 19.06.21 to 29.06.21 due to cyclone 'YAAS', Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000502/2021-2022 | 539/HSD(Camp) | 14/06/2021 | 25/06/2021 | M/S DATTA ENTERPRISE. | 3.67 | 3.67 | 100 | 0
30 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 15.06.21 to 22.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000516/2021-2022 | 553/HSD(Camp) | 14/06/2021 | 22/06/2021 | M/S NIRMAN CONSTRUCTION. | 4.91 | 4.91 | 100 | 0
31 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Sandeshkhali GP from 23.06.21 to 28.06.21 due to cyclone 'YAAS', Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000517/2021-2022 | 554/HSD(Camp) | 14/06/2021 | 20/06/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 3.68 | 3.68 | 100 | 0
32 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 15.06.21 to 20.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000525/2021-2022 | 562/HSD(Camp) | 14/06/2021 | 20/06/2021 | MONDAL & CO. (BASIRHAT). | 4.89 | 4.89 | 100 | 0
33 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Hingalganj GP from 21.06.21 to 26.06.21 due to cyclone 'YAAS', Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000533/2021-2022 | 570/HSD(Camp) | 14/06/2021 | 20/06/2021 | MONDAL & CO. (BASIRHAT). | 4.89 | 4.89 | 100 | 0
34 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places in Ward No.- 11, 12, 14 from 23.06.21 to 30.06.21 due to cyclone 'YAAS', Taki Municipality under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000536/2021-2022 | 573/HSD(Camp) | 14/06/2021 | 22/06/2021 | M/S RAJPATH CONSTRUCTION. | 3.45 | 3.45 | 100 | 0
35 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm & 75mm dia UPVC pipe at different places for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur-I & II GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000773/2021-2022 | 601/HSD(Camp) | 29/06/2021 | 06/07/2021 | M/S K.B.ENTERPRISE. | 3.72 | 0 | 0 | 0
36 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm dia UPVC pipe from N/H/O Santosh Sau to Roti Howly for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur- I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000774/2021-2022 | 602/HSD(Camp) | 29/06/2021 | 06/07/2021 | BADAL GHOSH. | 4.15 | 0 | 0 | 0
37 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 110mm dia UPVC pipe from N/H/O Balaram Mondal to Bablu Roy for the damage portion of AC/UPVC pipeline due to cyclone "YAAS" for Bhabanipur-I GP within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000775/2021-2022 | 603/HSD(Camp) | 29/06/2021 | 06/07/2021 | CHANCHAL ENTERPRISE & CO. | 4.41 | 4.41 | 100 | 0
38 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at different places due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000784/2021-2022 | 612/HSD(Camp) | 29/06/2021 | 06/07/2021 | CHITTA RANJAN MONDAL. | 4.24 | 4.24 | 100.02 | 0
39 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at N/H/O Samir Gayen & other diff. places due to cyclone 'YAAS' within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2021-2022 | 625/HSD(Camp) | 29/06/2021 | 06/07/2021 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.24 | 4.19 | 98.79 | 0
40 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000807/2021-2022 | 634/HSD(Camp) | 29/06/2021 | 06/07/2021 | LAHIRI CONSTRUCTION. | 4.38 | 4.34 | 98.94 | 0
41 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000808/2021-2022 | 635/HSD(Camp) | 29/06/2021 | 06/07/2021 | PRASANTA MITRA. | 4.38 | 4.34 | 99.02 | 0
42 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Korakati w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000845/2021-2022 | 649/HSD (Camp) | 30/06/2021 | 07/07/2021 | MD.SALIM GAZI. | 4.53 | 4.52 | 99.8 | 0
43 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Protection of UPVC pipe line by UC bullah pile at different places due to cyclone 'YAAS' within Gabberia w/s Scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000850/2021-2022 | 654/HSD(Camp) | 30/06/2021 | 07/07/2021 | PRITAM MUKHOPADHYAY. | 4.57 | 4.54 | 99.41 | 0
44 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by Laying of diff. dia. HDPE distribution pipe line due to cyclone ¿YAAS¿ Monoharpur Mouza within Hasnabad w/s scheme, Hasnabad Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000862/2021-2022 | 668/HSD(Camp) | 30/06/2021 | 07/07/2021 | ABDUL HAMID GAZI. | 4.47 | 4.47 | 100 | 0
45 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by Laying of diff. dia. HDPE distribution pipe line due to cyclone ¿YAAS¿ in Kalutala Mouza within Hasnabad w/s scheme, Hasnabad Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000863/2021-2022 | 669/HSD(Camp) | 30/06/2021 | 07/07/2021 | ABDUL HAMID GAZI. | 4.45 | 4.45 | 100 | 0
46 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by Laying of diff. dia. HDPE distribution pipe line due to cyclone YAAS in Purbachak Mouza within Hasnabad w/s scheme, Hasnabad Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000878/2021-2022 | 666/HSD(Camp) | 30/06/2021 | 07/07/2021 | ROY CHOWDHURY CONSTRUCTION. | 4.51 | 4.51 | 100 | 0
47 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Emergent supply of Drinking water by TATA 107/207/Mechanised Van with tank from nearest PHE sources to different places due to cyclone 'YAAS' within Abad Kuliadanga Desalination Plant covered area under, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001530/2021-2022 | 670/HSD (Camp) | 30/06/2021 | 13/07/2021 | M/S RAJPATH CONSTRUCTION. | 4.49 | 4.49 | 100 | 0
48 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 75mm dia UPVC pipe from N/H/O Palash Sardar to Sluice gate due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001532/2021-2022 | 672/HSD (Camp) | 30/06/2021 | 07/07/2021 | ABDUL ALIM MONDAL. | 4.94 | 4.93 | 99.94 | 0
49 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of waste water pipeline by laying of new 110mm dia UPVC pipe due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001533/2021-2022 | 673/HSD (Camp) | 30/06/2021 | 07/07/2021 | M/S DATTA ENTERPRISE. | 0.98 | 0.97 | 98.79 | 0
50 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of waste water pipeline by laying of new 110mm dia UPVC pipe due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001534/2021-2022 | 674/HSD (Camp) | 30/06/2021 | 07/07/2021 | M/S PROGATI ENTERPRISE. | 4.75 | 4.74 | 99.75 | 0
51 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Protection work of UPVC pipe line by Bamboo pilling at different places due to cyclone 'YAAS' within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001535/2021-2022 | 675/HSD (Camp) | 30/06/2021 | 07/07/2021 | ABDUL ALIM MONDAL. | 3.8 | 3.79 | 99.74 | 0
52 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90 mm & 75mm dia UPVC distribution pipe line from N/H/O Santosh Khara to Arindam Mondal due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001536/2021-2022 | 676/HSD (Camp) | 30/06/2021 | 07/07/2021 | ABDUL ALIM MONDAL. | 4.83 | 4.83 | 99.92 | 0
53 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Additional Restoration of waste water pipeline by laying of new 110mm dia UPVC pipe due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001538/2021-2022 | 678/HSD (Camp) | 30/06/2021 | 07/07/2021 | M/S PROGATI ENTERPRISE. | 4.46 | 4.45 | 99.73 | 0
54 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of different dia PVC distribution pipe line due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-13, 20 & 21), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001539/2021-2022 | 679/HSD (Camp) | 30/06/2021 | 07/07/2021 | M/S DATTA ENTERPRISE. | 4.85 | 4.85 | 100 | 0
55 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of different dia PVC distribution pipe line due to cyclone 'YAAS' within Sridharkati w/s scheme (Zone-27, 28 & 29), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001540/2021-2022 | 680/HSD (Camp) | 30/06/2021 | 07/07/2021 | M/S PROGATI ENTERPRISE. | 4.87 | 4.87 | 100 | 0
56 | NORTH 24 PARAGANAS |  | Barasat Division | Relief work in the form of Supply of Drinking Water through tanker and Disinfection of Tube Wells at Different GPS & wards in SANDESHKHALI-I Block & TAKI MUNICIPALITY duly affected by cyclonic storm | SM/09154 | Disaster | Acceptance cum work order for Restoration of pipeline by laying of new 90mm dia UPVC pipe from N/H/O Asim Das to Animesh Makhal due to cyclone "YAAS" within Bhabanipur w/s scheme, Hasnabad Block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001541/2021-2022 | 681/HSD (Camp) | 30/06/2021 | 07/07/2021 | ABDUL ALIM MONDAL. | 4.87 | 4.86 | 99.9 | 0
Total | [13 empty] | 252.54 | 243.66 | 96.49