## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000372/2022-2023 | 2437/BD | 22/08/2022 | 21/09/2022 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 32.03 | 72.13 | 100
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Joygram Bazar Idgah to near Pintu Molla Garage for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000528/2022-2023 | 1238/HSD | 20/07/2022 | 10/08/2022 | JESMINE ENTERPRISE. | 4.76 | 4.67 | 98.07 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Pintu Molla Garage to N/H/O Sahidul Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000529/2022-2023 | 1240/HSD | 20/07/2022 | 10/08/2022 | JESMINE ENTERPRISE. | 4.74 | 4.67 | 98.56 | 1
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Acceptance cum work order for Restoration of RCC drain from Near Julfikar Molla shop to N/H/O Sariful Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000530/2022-2023 | 1244/HSD | 20/07/2022 | 10/08/2022 | JESMINE ENTERPRISE. | 3.39 | 3.26 | 96.17 | 1
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Acceptance cum work order for Restoration of RCC drain from N/H/O Sahidul Molla to near Julfikar Molla shop for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000531/2022-2023 | 1246/HSD | 20/07/2022 | 10/08/2022 | JESMINE ENTERPRISE. | 4.76 | 4.42 | 92.78 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Kumarjole water supply scheme, Minakhan Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000597/2022-2023 | 2676/BD | 08/09/2022 | 07/12/2022 | JAL PRAVAHIKA PVT. LTD. | 260 | 259.94 | 99.98 | 1
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Formal work order for Construction of 400cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kumarjole water supply Scheme, Minakhan Block under Hasnabad Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2023-2024 | 2612/BD | 29/08/2023 | 28/08/2024 | S.S.ENTERPRISE. (BAMANGACHI) | 153.33 | 70.18 | 45.77 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation of Kumarjole water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001857/2023-2024 | 37/HSD | 09/01/2024 | 19/01/2024 | ABDUL ALIM MONDAL. | 0.83 | 0.4 | 48.02 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 2472/BD | 24/08/2022 |  | Resource Division | 8.92 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Kumarjole | SM/10302 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I & II under Bira-Rajibpur W/S Scheme, Khasdelpur W/S Scheme and Kumarjole W/S Scheme with Pump House No-I under Sadpur W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/002529/2023-2024 | 4490/EMD | 14/07/2023 | 13/08/2023 | EASTERN INDIA SALES & SERVICE | 74.22 | 9.63 | 12.98 | 58
Total | [13 empty] | 559.35 | 389.19 | 69.58