## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10503 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna programme within command area of Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000081/2022-2023 | 1492/BD | 25/05/2022 | 23/08/2022 | M/S S.S.ENTERPRISE. (SOUTH) | 164.51 | 125.08 | 76.03 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10503 | Retrofitting | Acceptance cum work order for Protection work for newly laid different dia. UPVC/DI distribution pipeline at different places in Daudpur Mouza of Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000850/2023-2024 | 2658/BD | 01/09/2023 | 01/10/2023 | M/S PROGATI ENTERPRISE. | 34.09 | 33.95 | 99.6 | 100
3 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10503 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within laukhali mouza due to erosion of soil for heavy rain fall during monsoon season within Daudpur w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000869/2023-2024 | 1055/HSD | 31/08/2023 | 10/09/2023 | ABDUL ALIM MONDAL. | 0.97 | 0.43 | 44.64 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Daudpur W/S Scheme, Sandeshkhali-II Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10503 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at head Work site within Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/001305/2023-2024 | 4378/BD | 10/11/2023 | 08/02/2024 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 23.09 | 10.54 | 45.66 | 100
Total | [13 empty] | 222.66 | 170.01 | 76.35