## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Formal work order for Protection work for newly laid UPVC pipe line at different places of Ghoshpur, Kalinagar & Roypur Mouza in connection with retrofitting of Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000040/2023-2024 | 1358/BD | 04/05/2023 | 03/06/2023 | UMWELT ENGINEER PVT.LTD. | 134.62 | 106.1 | 78.81 | 100
2 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Kalinagar W/s scheme (Zone-I), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000086/2022-2023 | 1570/BD | 01/06/2022 | 30/08/2022 | UMWELT ENGINEER PVT.LTD. | 274.51 | 255.99 | 93.25 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Acceptance cum work order for Repairing of pump house & boundary wall at PH No.-2 within Kalinagar w/s scheme (Old), Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000295/2023-2024 | 2106/BD | 19/07/2023 | 09/08/2023 | M/S GHOSH CONSTRUCTION. | 7.1 | 7.1 | 100 | 58
4 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Acceptance cum work order for Repairing of pump house & boundary wall at P.H.-3 within Kalinagar w/s scheme (Old), Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer |  | ORD/000299/2023-2024 | 2114/BD | 19/07/2023 | 09/08/2023 | GOBINDA DAS. | 7.21 | 7.21 | 100 | 59
5 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Ghoshpur mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000874/2023-2024 | 1060/HSD | 31/08/2023 | 10/09/2023 | M/S RAJPATH CONSTRUCTION. | 0.93 | 0.93 | 99.79 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Roypur mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000875/2023-2024 | 1061/HSD | 31/08/2023 | 10/09/2023 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0.96 | 99.51 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Kalinagar mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000876/2023-2024 | 1063/HSD | 31/08/2023 | 10/09/2023 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0.97 | 99.63 | 100
8 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Acceptance cum work order for Repairing of existing boundary wall and other allied works at Pump House No.-1 within Kalinagar w/s scheme (Old), Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000909/2023-2024 | 2720/BD | 05/09/2023 | 26/09/2023 | ABDUL ALIM MONDAL. | 9.09 | 9.09 | 100.01 | 100
9 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column & brick masonry & RCC Column structure at Head Work site & PH No- 3 within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001339/2023-2024 | 4435/BD | 10/11/2023 | 08/02/2024 | ABDUL HAMID GAZI. | 31.93 | 0 | 0 | 0
10 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) under command area of Kalinagar (Zone-I) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I | SM/10507 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Kalinagar water supply scheme (Z-I) in order to provide Har Ghar Jal Certification, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001730/2023-2024 | 429/BD | 09/02/2024 | 10/03/2024 | ABDUL ALIM MONDAL. | 70.78 | 17.36 | 24.53 | 75
Total | [13 empty] | 538.09 | 405.7 | 75.4