## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10557 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with retofitting of Kanmari w/s scheme (Zone-II), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000974/2022-2023 | 100/BD | 11/01/2023 | 11/04/2023 | M/S PROGATI ENTERPRISE. | 297.96 | 291.19 | 97.73 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10557 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Nazat mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001001/2023-2024 | 1084/HSD | 31/08/2023 | 10/09/2023 | M/S PROGATI ENTERPRISE. | 0.95 | 0.94 | 99.15 | 100
3 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10557 | Retrofitting | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Hatgachi mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/001002/2023-2024 | 1085/HSD | 31/08/2023 | 10/09/2023 | M/S PROGATI ENTERPRISE. | 0.94 | 0.94 | 99.86 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10557 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Kanmari mouza within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001813/2023-2024 | 231/HSD | 29/02/2024 | 10/03/2024 | SARKAR ENTERPRISE | 0.93 | 0.93 | 99.76 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10557 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Nalkora mouza within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001815/2023-2024 | 232/HSD | 29/02/2024 | 10/03/2024 | SARKAR ENTERPRISE | 0.93 | 0.55 | 59.66 | 100
6 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10557 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Hatgachi mouza within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001816/2023-2024 | 233/HSD | 29/02/2024 | 10/03/2024 | M/S PROGATI ENTERPRISE. | 0.94 | 0.47 | 49.97 | 100
7 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection under command area of Kanmari (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Barasat Division, PHE. Dte. (Phase I). | SM/10557 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Nazat mouza within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001818/2023-2024 | 234/HSD | 29/02/2024 | 10/03/2024 | M/S PROGATI ENTERPRISE. | 0.95 | 0.47 | 49.96 | 100
Total | [13 empty] | 303.59 | 295.49 | 97.33