## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | Augmentation | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Malancha w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2022-2023 | 2240/BD | 28/07/2022 | 27/08/2022 | M/S K.P.PAL. | 44.4 | 35.8 | 80.62 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Malancha water supply scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2022-2023 | 2449/BD | 23/08/2022 | 21/11/2022 | MONDAL & CO. (BASIRHAT). | 297.24 | 283.96 | 95.53 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | Augmentation | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Malancha w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000847/2023-2024 | 2655/BD | 01/09/2023 | 01/10/2023 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 50.24 | 43.92 | 87.42 | 37
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Malancha water supply scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001066/2023-2024 | 2863/BD | 20/09/2023 | 19/09/2024 | M/S B.K.ENTERPRISE. | 152.47 | 24.12 | 15.82 | 75
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 2577/BD | 31/08/2022 |  | Resource Division | 21.53 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 3363/BD | 17/11/2022 |  | Resource Division | 3.53 | 0 | 0 | 0
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000262/2022-2023 | 915/BD | 22/03/2023 |  | Resource Division | 22.12 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC | SM/10574 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II(Rep.) and III(New) (Zone-I) and Pump House No-I and II (Zone-II)(Rep.) under Malancha W/S Scheme District of 24 Pgs. (N) NIET NO. 32 OF EE/EMD OF 2022-23 (SL. NO. -15) | Assistant Engineer | Junior Engineer | ORD/001675/2022-2023 | 1013/EMD | 09/03/2023 | 08/04/2023 | MAHADEV ENTERPRISE | 66.24 | 0 | 0 | 40
Total | [13 empty] | 657.77 | 387.8 | 58.96