## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chandpara Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000831/2022-2023 | 3629/BD | 12/12/2022 | 12/03/2023 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 525.18 | 367.15 | 69.91 | 88
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chandpara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/000885/2023-2024 | 2699/BD | 04/09/2023 | 04/10/2023 | NADIA TUBEWELLS | 16.16 | 5.3 | 32.8 | 100
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chandpara Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001114/2023-2024 | 2937/BD | 27/09/2023 | 27/10/2023 | JOY GURU ENTERPRISE | 16.12 | 7.44 | 46.17 | 100
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Acceptance cum work order for Renovation & repairing of Boundary wall at Head work site for Augmentation of Chandpara water Supply scheme, Gaighata Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001479/2023-2024 | 4412/BD | 10/11/2023 | 09/01/2024 | BHABANI ENTERPRISE. | 13.44 | 6.68 | 49.72 | 100
5 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Acceptance cum work order for Renovation and repairing of Boundary wall at 3rd Tube Well site and Construction of Approach Road at 3rd Tube Well site and Head work site under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001555/2023-2024 | 41/BD | 04/01/2024 | 27/01/2024 | ROY ENGINEERS. | 7.4 | 0 | 0 | 0
6 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001566/2023-2024 | 63/BD | 05/01/2024 | 04/02/2024 | SAMBHU RAY CHOWDHURY. | 6.02 | 2.74 | 45.49 | 92
7 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Formal work order for Dismantling and Cement Concreting of existing Cement Concrete Road for laying rest part of UPVC pipes within command area and Drum Sheet Walling for supporting other UPVC Pipes along the NH 35 for Augmentation work at Chandpara W/S Scheme under Gaighata block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002017/2023-2024 | 808/BD | 12/03/2024 | 10/06/2024 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 112.22 | 22.51 | 20.06 | 50
8 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. |  |  | ORD/002275/2023-2024 | 841/Bon | 01/11/2023 | 24/11/2023 | M/S SAYAN ENTERPRISE. | 4.59 | 0 | 0 | 0
9 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chandpara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002860/2021-2022 | 144/Bon | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.05 | 0 | 0 | 1
10 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Route Survey, Design Drawing & Preparation of DPR for Chandapara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002898/2021-2022 | 143/BON | 18/02/2022 | 05/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.05 | 4.04 | 99.72 | 1
11 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chandpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002928/2021-2022 | 537/Bon | 03/11/2021 | 24/11/2021 | SAMBHU RAY CHOWDHURY. | 2.52 | 2.47 | 98.01 | 1
12 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Repairing & Renovation of 01No. Pump House and allied works at Chandpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002936/2021-2022 | 634/BON | 31/12/2021 | 21/01/2022 | SAMBHU RAY CHOWDHURY. | 1.26 | 1.14 | 90.91 | 1
13 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 1360/BD | 13/05/2022 |  | Resource Division | 11.96 | 0 | 0 | 0
14 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 3657/BD | 13/12/2022 |  | Resource Division | 31.17 | 0 | 0 | 0
15 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Ground water based piped water supply scheme for Chandpara to accommodate FHTC | SM/10587 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I, II and III (Rep) under Chikanpara W/S Scheme and Pump House No.I, II and III under Chandpara W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001167/2023-2024 | 4795/EMD | 09/08/2023 | 08/09/2023 | DAS ENTERPRISE (M) | 78.21 | 0 | 0 | 0
Total | [13 empty] | 834.35 | 419.48 | 50.28