## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Nalkora water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 3588/BD | 08/12/2022 | 07/01/2023 | SARKAR ENTERPRISE & CO. | 69.53 | 62.47 | 89.85 | 99
2 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Nalkora W/S Scheme including increasing the height of back wash tank at Basirhat - I Block under Basirhat Sub Division, PHE Dte. Capacity - 10.81 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002026/2023-2024 | 920/BD | 15/03/2024 | 14/05/2024 | MONDAL PRECISION PVT.LTD | 23.26 | 0 | 0 | 60
3 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Route Survey, Design Drawing & DPR Preparation for NALKORA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002858/2021-2022 | 202/ BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.79 | 2.61 | 93.6 | 1
4 | NORTH 24 PARAGANAS |  | Barasat Division | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2022-2023 | 3819/BD | 23/12/2022 |  | Resource Division | 23.93 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of ground water based piped water supply scheme for Nalkora to accommodate FHTC | SM/11524 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Rep.) under Nalkora W/S Scheme and Pump House no-I and II (Zone-I)(Rep.) Chhayagharia W/S Scheme with Pump House No-I and II (Zone-II)(Rep.) under Sindrani W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/003334/2023-2024 | 4812./EMD | 09/08/2023 | 08/09/2023 | WEST BENGAL ENGINEERING CO. | 78.21 | 0 | 0 | 17
Total | [13 empty] | 21537.47 | 65.08 | 0.3